## Sheet1
No. |  | Last | First | Address | City | State | Zip | Phone |  | Per CBE | Acquired | Commit'd | Spent | Commit'd |  | Short Comment
| Tax ID | Name | Name | grantor | grantor | gtr | gtr | Contact | Gross Ac | Net Ac | Net Acre | Net Acre | Money | Money | LOC
1 | 57-20-00-0-051 | Eidemiller | John Phillip, III, Rev Liv | RR 2, Box 1077 | New Alexandria | PA | 15670 | 724-668-7304 | 83.2 | 36.1775 | 36.1775 |  | 144.71 |  | GLEP | SIGNED 6-16-2005: $4 B $4 rent, 1/8th, 5 yrs. 0305/099.110-15-05 Note Continue to wait until Hutson & water disposal issues handled. 9-13-04: Firm in demand that wants 1/7th roy., and his well to be comprised of only his 34 ac. (as a unit); Suggested his demands be met, or move well. If initial drilling occurs on another tract-may change his position. 9-7-04 wants to be his own unit, 1/7th roy..Researching his additional 2+ acres claimed to possibly add to lease and let cool his heels for a while. 08-19-04, Met several hours,inclined to lease. Wants to see a more precise plotting of location. Requested GPS coorindinates. FU mtg 8-23-04. 11-21-03 Hes unhappy about owning less than 100% coal. Mail him a form; call him after 12-1-03. Offered $2/ac bonus, $4/ac/yr rental, 1/8th roy. for 5 yr term with extension option.
1 | 57-20-00-0-051 | Ondra | Jan |  |  | PA |  |  | 0 | 47.0225 | 47.0225 |  |  |  | GLEP | SIGNED by CB Energy, Inc. and assigned to GLEP.
1a | 57-20-50-90-120 | Hutson (Freeport seam; severed coal under Jerome Eidemiller property) | Bruce | Apt. 101, 1999 Green St. | San Francisco | CA | 94123 | 415-931-9431, cell & primary Ph. 415-613-3060 | 164.5 | 54.285 | 54.285 |  | 434.28 |  | GLEP | SIGNED $8/ac B, $8/ac/yr rent, 1/8th, 5 yrs. 10-30-04 rec'd pkg will sign and return. 10-30-04 LVM. 10-28-04 LVM. 10-22-04 sent new lease. 10-14-0 FU to James R. Cascio, atty (814-445-7948),reviewed doc's & needed to speak with Hutson to approve;wants to strike warranty of title. 9-14-04: has a full pkg he agreed to sign. called stating he would;not been able to contact. 8-21-04: Unavailable. DBV 41, Pg 292, He is sole heir of Gertrude Hutson and Elizabeth Ball. This interest is the Freeport Coal seam only, which represents 33.33% of the estimated production value of all the coals combined (as per CB Energy calculations).
1a | 57-20-50-90-120 | unknown | [13 empty] | SIGNED by CB Energy, Inc. and assigned to GLEP.
2 | 57-19-00-0-041 | Kepple | James L. & Michelle L. | RD 2, Box 842 | New Alexandria | PA | 15670 | 724-668-8954 | 193.821 | 193.821 | 193.821 |  | 397.65 |  | GLEP | SIGNED 11-12-03: $2/ac bonus+Q12, $4/ac/yr rental, 1/8th roy., 5yr primary with 5 yr renew option, Riders: Consult on access & pipeline locations & Restricted operation areas shown on Exh. "A" (checked with Carlson prior to). No free gas. 002/23141,
3 | 57-19-00-0-119 | Kepple | James L. & Michelle L. | RD 2, Box 842 | New Alexandria | PA | 15670 | 724-668-8954 | 4 | 4 | 4 |  | 8 |  | GLEP | SIGNED 11-12-03 (see terms above)
3a | 57-19-00-0-118 | Kepple | James L. & Michelle L. | RD 2, Box 842 | New Alexandria | PA | 15670 | 724-668-8954 | 2.18 | 2.18 | 2.18 |  | 4.36 |  | GLEP | SIGNED 11-12-03: $2 b, $4/ac/yr rent, 1/8th roy., 5yr prim. w/ 5 yr opt, Consult on access & pipeline locations & Restricted operation areas shown on Exh. "A"
4 | 57-20-00-0-013 | Carr | Charles S. & Betty Lou | 201 Shady Road | New Alexandria | PA | 15670 | 724-668-7343 | 165.66 | 165.66 | 165.66 |  | 993.96 |  |  | 04/06/07: SIGNED $6/ac Non-Drilling CBM Gas Lease w/o ROWA 03/20/07: prep Non-Drilling CBMGL pkg; attempted to set up mtg 03/09/07: please change address to 201 Shady Road 03/06/07: Sent mail out letter offers with supporting information 03/01/07: Mr. Carr was very uninterested; Offered wife Non-Drilling CBMGL and explained horizontal drilling; she took my information DON'T CONTACT TIL DISCUSSED. 1763/548 & 3590/59, 9-15-04:Position unchanged. 9-7-04: spoke w/ Mr. C. Carr, Jr., said he & his group, want lease for all O&G, CBM or nothing, but note til after crops in (Oct or Nov). Will attempt to get "requirements". Groups has approx. 307.5 CBM ac's & at least 530 O&G ac's all abuts. 9-2-03: Mtg w/ Charles Carr, Jr & Sr. offered Coal rights for 5 yr pd up lease & row from son and $4/ac bonus, $4/ac/yr, 1/8, 5yr + 5yr optn from father. attentive, but non committal; wants to speak with atty. 8-19-04, spoke w/ Mr. Carr and agreed to mtg to include his son to discuss in detail. 11-18-09 mail Lease form (to son) w/ cover ltr offer $2/ac bonus, $4/ac/yr rental, 1/8th roy. & CB Energy offer to exchange QCD for coal rights for lease of his & father tracts. Son requested send new lease form; call back in week. Last Contact 10-30-03 @ 5:45pm. 2-1-05 Title completed.
5 | 57-20-00-0-014 | Carr | Charles S., Jr. & Marilyn J. | RD 2, Box 970 | New Alexandria | PA | 15670 | 724-668-2372 | 66.5 | 0 | 66.5 |  |  |  |  | DON'T CONTACT UNTIL DISCUSSED. 10-30-04 spoke with wife, not in call after 6:00 pm. SEE note above for Carr Sr. for current activity. 11-18-03 requested okay to mail Lease form with cover ltr offer $2/ac bo, $4/ac/yr rental, 1/8th roy. & CB Energy offer to exchange QCD for coal rights for lease of his & fathers tracts. 2566/246 (CB Energy got QCD from Consolidated for this Tr., will exchange for Lease from both) Last Contact 10-31-03 @ 9:05 am, spoke with Marilyn, "men out harvesting" best time to call, "next week at lunch time", or "a rainy day" harvest should be finished in a week.
5 | 57-20-00-0-014 | GLEP | GLEP | [5 empty] | 0 | 66.5 | 66.5 |  |  |  |  | 03/14/07: needs to be marked acquired; its owned by GLEP Great Lakes Energy Partners, LLC acquired the coal rights on this tract from CB Energy, Inc. These rights were offered to E. Carr in exchange for CBMGL on this tract & his fathers.
6 | 61-03-00-0-002 | Heinnickel Farms, Inc. | Heinnickel, Phillip contact | RD 9, Box 317 | Greensburg | PA | 15601 | 724-837-9254 | 164 | 164 | 164 |  | 984 |  | GLEP | 02/23/07: SIGNED $6/ac. completed processing signed pkgs; Farm in Unity Twp. & individual tracts; organized file, created purchase reports, highlighted maps, GLEP/GWM copies 02/15/07: prepared Non-Drilling CBM Gas Lease w/o ROWA pkg for property in Unity Twp., attended meeting as Notary w/ GWM 02/07/07: Sharon gave me last bits of information, her cell is (724) 309-6055, will sched. mtg to execute individual package 02/05/07: left msg for Philip and William Delivered pkg to FEDEX 12/22/06: Delivered pkgs to Heinnickel Farms, Inc 12/14/06 set apt with Philip H. to meet with him and Alquin for final review 8AM 12-18-06 (“they have several issues” & I requested signing by 12-22-06) 12/07/06 OFFERED: $8/ac bonus, $8/ac rental, 1/8th royalty, 5 yr lease same heavily modified CBE lease form; completed draft of CBE lease form & memo approved by B. Benjamin to be delivered by T. Henry11/22/06: @ 8AM Meeting with Philip & Alquin Heinnickel; reviewed new horizontal drilling program and discussed their requirements “want what is on the lease they signed with CB Energy, Inc.”; was told we do not give free gas11/17/06: contacted Philip Heinnickel requested meeting to set up signing of their remaining acreage; apt set for 8AM 11-22-06 3575/560 & 2008/044, HOLD OFF CONTACT at this time (see prior notes). Last Contact 10-30-03 He wanted to "see the process" and production from existing leased AC before committing the remaining AC. 10-29-03 Unavailable, call back later. 10-30-03. 10-27-03 Spoke to Alquin Heinnickel who referred me to his brother Phillip to discuss energy issues.2008/0044, see comment above
7 | 61-03-00-0-034 | Heinnickel Farms, Inc. | Heinnickel, Phillip contact | RD 9, Box 317 | Greensburg | PA | 15601 | 724-837-9254 | 1.3 | 1.3 | 1.3 |  | 7.8 |  | GLEP | 2308/906, see comment above
8 | 61-03-00-0-001 | Heinnickel Farms, Inc. | Heinnickel, Phillip contact | RD 9, Box 317 | Greensburg | PA | 15601 | 724-837-9254 | 10.2 | 10.2 | 10.2 |  | 61.2 |  | GLEP | 2278/0495, see comment above
9 | 50-10-080 | Heinnickel Farms, Inc. | Heinnickel, Phillip contact | RD 9, Box 317 | Greensburg | PA | 15601 | 724-837-9254 | 271.8 | 271.8 | 271.8 |  | 1630.8 |  | GLEP | 2008/044, 3575/560, 3586/123, see comment above
10 | 50-10-00-0-123 | Heinnickel Farms, Inc. | Heinnickel, Phillip contact | RD 9, Box 317 | Greensburg | PA | 15601 | 724-837-9254 | 69.771 | 69.771 | 69.771 |  | 418.626 |  | GLEP | 2143/1016, 3586/123, see comment above
11 | 50-10-00-0-158 | Heinnickel Farms, Inc. | Heinnickel, Phillip contact | RD 9, Box 317 | Greensburg | PA | 15601 | 724-837-9254 | 69.493 | 69.493 | 69.493 |  | 416.958 |  | GLEP | 3586/123, 3587/120, see comment above
12 | 50-10-00-0-284 | Heinnickel Farms, Inc. | Heinnickel, Phillip | RD 9, Box 317 | Greensburg | PA | 15601 | 724-837-9254 | 129.92 | 129.92 | 129.92 |  | 779.52 |  | GLEP | 2008/044, 3586/123, see comment above
13 | 50-10-00-0-150, 50-10-00-0-283 | Heinnickel | William and Sharon | [5 empty] | 10.965 | 10.965 | 10.965 |  | 65.79 |  | GLEP | 02/12/07: SIGNED $6/ac Non-Drilling CBM Gas Lease w/o ROWA
14 | 57-21-00-0-034 | Sloskey | Michael D. & Edna Sharon | RD 2, Box 1150 | New Alexandria | PA | 15670 | 724-668-2906 | 16.1 | 16.1 | 16.1 |  | 32.2 |  | GLEP | SIGNED 11-22-03 $2ac B, $4 rent, 1/8th roy., 5yr w/ 5 yr opt term. Added consult on access/pipeline locations & damages covers water well. No free gas.
15 | 57-21-00-0-037 | Sloskey | Michael D. & Edna Sharon | RD 2, Box 1150 | New Alexandria | PA | 15670 | 724-668-2906 | 1.8 | 1.8 | 1.8 |  | 3.6 |  | GLEP | SIGNED 11-22-03: $2/ac Bonus, $4/ac/yr rental, 1/8th roy., 5yr with 5 yr option term. Added consult on access/pipeline locations & damages covers water well. No free gas.
16 | 57-21-00-0-033 | Carr | Edwards S. & Robert | 1 Limerick Rd. | Herminie | PA | 15637 | no phone listing | 3.213 | 3.213 | [5 empty] | 12/18/06: Attempted contact. 12/04/06: Mailed offer letter & supporting information 6-17-05 Offered non-Surface lease.$4/ac bonus, $ 4/ac/yr rental. 1/8th, 5yr term, discuss lease with sisters ; not signing, thinking about selling tract. 6-12-05 He wants sister to review lease; gave him deadline Monday 6-13-05.6-09-05 car there, but nobody would answer door 6-08-05 has no phone.5-18-05 mtg,Robert wants to discuss with siblings. 3484/0356 11-22-03, no contact to-date.
17 | 57-21-00-0-052 | Galando | Alice F. | RD 2, Box 1142 | New Alexandria | PA | 15670 | 724-668-7115 | 1.5 | 1.5 | 1.5 |  | 30 |  | GLEP | Signed 5-11-05 $4/ac B $4/ac R (PAID-UP), 1/8th, 5yr, term,non surface. 3752/10041
18 | 57-21-00-0-032 | Galando, Life Estate | Helen | RD 2, Box 1142 | New Alexandria | PA | 15670 | 724-668-2886 | 1.9 | 1.9 | 1.9 |  | 38 |  | GLEP | Signed 5-18-05 $4/ac B $4/ac R (PAID-UP), 1/8th, 5yr, term,non surface use lease.
19 | 61-01-00-0-001 | Berger | Paul E. & Roxanne | RR 1, Box 511 | New Alexandria | PA | 15670 | 724-668-2045 & 724-668-8839 | 28.559 | 28.559 | 28.559 |  | 57.12 |  | GLEP | SIGNED 11-6-03 $2ac b $4 rent, 1/8th roy., 5yr prim w/ 5 yr re opt, drilling restricted around home/barn area on plat attached. No free gas.
20 | 61-01-00-0-006 | Berger | Paul & Roxanne | RR 1, Box 511 | New Alexandria | PA | 15670 | 724-668-2045 & 724-668-8839 | 67.9 | 67.9 | 67.9 |  | 135.8 |  | GLEP | SIGNED 11-6-03: $2/ac bonus, $4/ac/yr rental, 1/8th roy., 5yr primary with 5 yr rew option, drilling restricted around home/barn area shown on plat attached. No free gas. 3045/0084 & 3406/0338,
21 | 57-20-00-0-016 | Long, et al | Phillip G. | 341 Bardine Road | New Alexandria | PA | 15670 | (724) 668-2954 | 0 | 180 | [5 empty] | 03/12/07: left GLEP notice 03/06/07: Sent mail out letter offers with supporting information 03/01/07: left message 02/26/07: call wed evening for apt Thurs/Fri; Cell (724) 331-1776 02/06/07: completed bring down and plotted tracts: Conservation Easement permits horizontal drilling 11/29/06: Updated grantor information.
22 | 57-20-00-0-080 | Devinney | William C. & Wanda M. | RD 2, Box 705 | New Alexandria | PA | 15670 | 724-668-7073 | 53.7 | 53.7 | [5 empty] | 03/06/07: Sent mail out letter offers with supporting information 12/11/06: won't have any mtg. "If you want to buy the place, then we'll make a deal" 11/27/06: William away until 12/11/06; follow up then for mtg w/ brothers 2479/118
23 | 57-20-00-0-020 | Devinney | William C. & Wanda M. | RD 2, Box 705 | New Alexandria | PA | 15670 | 724-668-7073 | 1.7 | 1.7 | [5 empty] | See notes above.
24 | 57-20-00-0-081 | Devinney | David E. & Joyce | RD 2, Box 710 | New Alexandria | PA | 15670 | 724-668-2162 | 55.3 | 55.3 | [5 empty] | 03/06/07: Sent mail out letter offers with supporting information 02/26/07: left message for David & his wife See notes above.
25 | 57-20-00-0-077 | Devinney | David E. & Joyce | RD 2, Box 710 | New Alexandria | PA | 15670 | 724-668-2162 | 2.57 | 2.57 | [5 empty] | See notes above.
26 | 75-21-00-0--023 | Perrone Family Limited Partner |  | 4719 W. Lawnview Avenue | Pittsburgh | PA | 15227 | (C) (412) 418-0176, (O) (412) 881-9205 | 208 | 208 | [5 empty] | 03/16/07: took lease package for review; deadline 3/22/07 03/15/07: completed CBMGL pkg, proof/print, mtg 3/16/07 11:00am 03/13/07: add address: 4719 W. Lawnview Avenue, Pittsburgh, Pennsylvania 15227 and his office number (don't delete his cell) 412-881-9205; printed acquisition deed, calculated acreage, completed bounded bys, created highlighted map 03/06/07: add cell number 412-418-0176; call Tuesday 3/13/07 to schedule meeting 3/14/07 with Bruce Perrone 02/08/07: hone mtg for GWM sched 2/12 10am 02/01/07: Spoke w/ Bruce; call 2/8/07 to schedule a mtg w/ GWM the following week 01/26/07: left msg for Bruce 11-17-03 Offered $4/ac B, $4/ac Rl, 1/8th roy., 5yr term, riders 1,2, 3. 2 .Not willing to sign a lease "not wanting land disturbed." Mailed ltr with plat to select restricted areas. 3380/598, Per Carl Carlson, suggested mail TOPO to Bruce let them mark restricted areas; wait for pilot proj. for spacing needs. Last Contact 10-24-03 @ 12:00 PM, Bruce Perrone, willing to reopen the issue to family if GLEP would be willing to designate restricted areas of surface operations. LM for Carl Carlson.
27 | 57-21-00-0-044 | Perrone Family Limited Partner |  | 4719 W. Lawnview Avenue | Pittsburgh | PA | 15227 | (C) (412) 418-0176, (O) (412) 881-9205 | 86 | 38 | [5 empty] | 03/16/07: took lease package for review; deadline 3/22/07 03/15/07: completed CBMGL pkg, proof/print, mtg 3/16/07 11:00am 03/13/07: add address: 4719 W. Lawnview Avenue, Pittsburgh, Pennsylvania 15227 and his office number (don't delete his cell) 412-881-9205; printed acquisition deed, calculated acreage, completed bounded bys, created highlighted map 03/06/07: add cell number 412-418-0176; call Tuesday 3/13/07 to schedule meeting 3/14/07 with Bruce Perrone 02/09/07: left a message for Bruce to schedule phone conference for GWM for 02/12/07 at 4:00 p.m. 3389/598 See Carl Carlson suggestion above. 11-17-03 mailed ltr with plat for them to select restricted areas. Last Contact 10-24-03 Willing to reopen the issue to family if GLEP would be willing to designate restricted areas of surface operations. LM for Carl Carlson.
27 | 57-21-00-0-044 | unknown | [7 empty] | 48 | [5 empty] | unknown coal owner
28 | 57-19-00-0-050; 57-19-00-0-051; 57-19-00-0-161 | Smith | William R. & Carol S., h/w | 128 Bliss Lane | New Alexandria | PA | 15670 | parents 724-668-7745 Son 724-668-0059 | 123.156 | 123.156 | 123.156 |  | 1477.38 |  | GLEP | SIGNED : $12 bo. $10 rent, 1/8th roy., 5yr term, w/ blanket row.1-13-06 wants 3/16 roy., before he will sign.1-6-06 Offered $8/ac bo., $8/ac/yr rent, 1/8th roy., 5yr term, w/blanket row. FU 1-10-05.10-3-05 mtg, wants 3/16 roy. & $10 rent.8-19-05wants to check his other tracts, before signing FU 8-25-05.8-13-05 Offered $4/ac bonus, $4/ac/yr rent, 1/8th roy...
29 | 57-23-00-0-048; 57-23-00-0-088 | Smith | William R. & Carol S., h/w | 128 Bliss Lane | New Alexandria | PA | 15670 | parents 724-668-7745 Son 724-668-0059 | 116.598 | 116.598 | 116.598 |  | 1399.18 |  | GLEP | SIGNED: See notes on tract above.5-16-05 Wants to wait until Atlas Drilling finish activity on property.3-23-05 Atlas Drilling on property, not wanting to do anything with CBM now, maybe in 6 months.101/568, Parents converted to son since last mtg. 8-21-04:LM. 11-22-03 met with M/M Smith, reviewed and left sample CBML form, "will lease if GLEP leases all, but want to talk to Frye". Contact 11-5-03:
30 | 57-24-00-0-009 | DiBerardino | Robert | 205 Bardine Road | New Alexandria | PA | 15670 | 724-837-0709; Son's cell (248) 521-3215 | 73.5468 | 73.5468 | [5 empty] | 03/20/07: lessors son called me to discuss proposal while I was currently in a mtg. I tried to return call but no answer. 03/15/07: spoke with lessor, was informed it was sons decision even though Robert is the own who signs the contracts. Was given sons number but no answer. 03/13/07: mailed updated offer letter and list of signed landowners, add son Steve's cell# 248-521-3215 11/30/06: "not prepared to lease anything from our property at this time" 11/29/06: left msg 11/27/06: potential signing tonight: no answer; left msg 11/20/06: Offered $8/ac Nonsurface CBM Lease w/ ROWA- saw no problem with it; won't sign until son approves; faxed to him in MI 11/18/06: prep pkg, apt. set for 11/20/06 6-29-06 him and 2 sons will make the decision; sons will be home next week, FU 7/6/06 6-22-06 MOL 8-13-05 Offered $4/ac bonus, $4/ac/yr rental, 1/8th roy., 5yr term, riders 1,2, 3, considering, wants FU on 8-22-05. 6-18-05 Unvailable.5-25-05, mtg, with son, stop by on Monday's to speak with brother. 5-3-05 Spoke with son, Lessor hard to catch at home.4-18-05 mtg, wants me to meet with his son Sat 4-23-05 4-15-05 3361/464, Last calls 10-28 to Tim Diberadino (distant cousin), attempting to contact, no phone listing.
31 | 57-24-00-0-031 | Frye | Wayne C. & Hope L. | RD 9, Box 264 | Greensburg | PA | 15601 | 724-668-2833 | 139.8 | 139.8 | 139.8 |  | 279.6 |  | GLEP | SIGNED 11-6-03: $2/ac B, $4/ac yr R, 1/8th roy., 5 yr primary no renewable, Riders: indemnification & consult on roads & pipeline locations. No free gas.
32 | 57-20-00-0-059 | Herman, McNaughton, Murphy, Co-Tr's under Bowman Fam Irrevoc. Tr. Dated May 16, 2003 | Debra Dawn Tamie Lee Lysa Renee |  |  |  |  | 724-668-2198 Charles & Martha's phone | 53.16 | 53.16 | [5 empty] | 03/09/07: mailed offer letter and updated list of signed landowners 02/26/07: no answer and no machine 12/11/06: Mrs. Bowman said they won't do anything with methane because we don't heat homes. Supposedly their neighboring town is heated by methane and we claim it can't be done. 11/30/06: mailed offer ltr 8-13-05 Offered $4/ac B, $4/ac/yr R, 1/8th roy., 5yr term, riders 1,2, 3;undecided at this time, she would call me when she wants to lease.6-13-05 spoke w/ daughter, LM 6-2-05 LM. 3756/646, 3756/649 & 3757/1 all 5.0304ac, 1.16ac & 46.97ac conveyed by QCD instr. Number 200307070052904, Last call 11-5-03 various times, no answer. 10-28-03 @ 4:27pm, left VM on recorder.
33 | 57-20-00-0-017 | DeVinney | Dorothy, a widow | [12 empty] | 12/15/07: Not attmpting to acquire.
33.1 | 57-20-00-0-113 | Altieri | Yony J. | 186 DeVinney Road | New Alexandria | PA | 15670 | 724-668-0001 | 1.587 | 1.5869 | [5 empty] | 03/12/07: add 1.587 to surface acres 03/02/07: Offered $6.00 per ac Non-Drilling CBMGL w/o ROWA; Wife said they are not interested 02/05/07: Added
34 | 57-19-00-0-009 | Wright | John C. & Suzanne K., h/w | RD4, Box 317 | Greensburg | PA | 15601 | 724-836-0620 | 86.693 | 86.693 | [5 empty] | 03/05/07: prep CBMGL pkg and left a message 03/02/07: call back 3/5/07 for mtg 02/26/07: left message 02/05/07: sent mail out information and offer Left messages 12/11/06: Left msg following up with offer ltr and asking for mtg 12/05/06: Prepared mail out letter offers; mailed with supporting information 11/30/06: unavailable 11/29/06: left msg w/ wife - best time to reach Lessor is b/t 8-10am 11/22/06: Attempted contact, left message. 4-2-06 Offered $8B/$8R, 1/8th roy., 5yr term, "not interested, not willing to disturbed land"; 3-13-05 Offered $4/ac bonus, $4/ac/yr rental, 1/8th roy., 5yr term, riders 1,2, 3. "No, not wanting land disturbed; not willing to discuss futher". 3-28-05 not wanting land disturbed.3-23-05 LM.3-18-05cld, LM.3-11-05 Wants to discuss with wife. LM.3-07-05, reviewed & assigned; 2-16-05 title completed,edited 3-07-05. Subject to Storage Easement and Agreement to CNG dated 4-24-1998, DBV 3579/433, 1,200' to 2,400'.
35 | 57-24-00-0-024 | Slezak | Fred J. & Margaret S., h/w | POB 407 | New Alexandria | PA | 15670 | home- 724-668-2539 office- 724- 668-7358 Cell 724-244-5229 | 93.785 | 93.785 | [5 empty] | 02/26/07: he does not want a lease on his property right now 02/22/07: mtg to sign 2/24/07 2:00 pm 02/20/07: left message at the office and a message on his voice mail 02/19/07: left message at office 02/16/07: call him 2/19/07 in the morning to schedule signing 02/12/07: attended mtg w/ GWM- offered $6/ac Non-Drilling CBMGL w/o ROWA - committed to execute at the end of the week 02/09/07: Prepared Non-Drilling CBMGL pkg 6-29-06 LM 6-22-06 MOL. 4-22-06 LM. 4-11-06 wants more time.FU 4-19-06.4-8-06 Busy, FU 4-10-06 for mtg 4-3-06 took lease to review, will FU 4-7-06.4-2-06 booked mtg 4-3-06. 4-1-06 mtg, wants FU call on 4-3-06 to book mtg. 5-5-05 delivered offer ltr: Offered $4/ac b, $4/ac/yr rent, 1/8th roy., 5yr term, extensive riders: not willing to sign 5 year lease. Will only sign 3 year term lease & pipeline location restriction. 4-21-05 wants 3 year lease & exact location of ROW. 4-15-05 Cancelled mtg. FU 4-0-08 Cancel mtg, booked for 4-11-05.
36 | 57-20-00-0-012 | Marcheleta | Ralph F. & Karen, h/w | 285 Kemp Road | New Alexandria | PA | 15670 | 724-668-2354 | 39.5 | 39.5 | [5 empty] | 03/20/07: attempted to contact attorney but was not in office and did not return my call. Lessor called and wanted to meet for dinner at 6 p.m. and talk about contract. I informed them both that this was the last offer and they wouldnt have a chance to participate if they didnt now. Lessors refused without working it out with attorney first but they cant reach their attorney either. 03/19/07: attempted to contact attorney but no answer, lessor called late in the evening to ask if I had talked to his attorney but he didnt return my call. Will follow up tomorrow. 03/15/07: spoke with lessor to see if he contacted attorney but stated he couldnt get ahold of him. Lessor gave me the number to call attorney. I contacted attorney and he stated he sent three copies of the modified contract to us but couldnt remember the changes he wanted. Attorney was told his modifications would be denied but he wanted to call me back Monday 3-19-07 03/14/07: stopped by lessors at 4:30 p.m. and wife called husband on cell phone and let me talk to him. He wanted me to come back out at 5:30. After a two hour meeting he stated he didnt want to sign the contracts without telling his attorney he is doing so. Lessor is supposed to sign tomorrow at 5:30 if attorney doesnt have any strong objections. -Updated, printed, and proofed package prior to meeting. 02/26/07: he hasn't heard back from his attorney yet; he doesn't want to make a decision 01/23/07: wants to submit the lease Conti writes - if its rejected "then we'll talk again" 01/22/07: unavailable, number busy all evening 01/19/07: explained the custom lease from att. Conti will be rejected (Paluzzi's has already) - informed him of his update in AC concerning both tracts, gave him an alternative to our lease; follow up Mon/Tues if he wants to pursue before 2/1/07 01/17/07: had title run on 10.5ac tract; completed bounded by, corrected lease package, emailed to GWM, left message for Lessor 01/12/07: phone conversation with Mr. Marcheleta: he is trying to deliver his lease to attorney Conti, he leaves February 1st for Florida for two months. I asked that this be resolved before he leaves; he said a decision will be made soon. He wants another meeting because he has questions but will call me to schedule. Also concerned about the 10 acres he is only the surface owner. 01/11/07: left message 01/09/07: left msg w/ wife 01/05/07: left GLEP notice on door 12/20/06: Left message. 12/15/06: left msg asking to schedule signing 12/04/06: Brother is reviewing lesae (he's in O&G industry): stated they want to sign 11/30/06: left msg 11/29/06: Offered $6/ac nonsurf CBMGL w/o ROWA 11/27/06: prep/print pkg 11/20/06: MTG 11/28 10am 11/18/06: Call back Monday morning to sched mtg with husband; completed bring down 4-24-06 MTG, offered $12B/8R, 1/8roy, 5yr, wants to sign; wife won't, " not wanting pipe on tract." Took updated signed LO sheet/GLEP info. FU mtg 5-8-06. 4-22-06 LM. 8-13-05 LM. 6-2-05 Wants to wait until something happens with this ordinance, before make a decision. Offered $4/ac b, $4/ac/yr rent, 1/8th roy., 5yr term, riders 1,2, 3. response, wants to wait; neighbors are upset about CBM project. 5-18-05 Unavailable. 5-5-05 undecided FU 5-16-05. 4-11-05 wants more time to review lease. 3-16-05 Going out town, booked mtg 3-29-05. 3-12-05 reviewed & assigned; 1-31-05 title completed, edited 3-11-05.
45 | 57-23-00-0-058 | Frenchek | William T. & Karin M., h/w | 1041 Orchard Avenue | Greensburg | PA | 15601 | 724- 837-9030 | 45 | 45 | 45 |  | 180 |  | GLEP | SIGNED 3-29-05. $4/ac B $4/ac/ yr R, 1/8th, 5yr, term.3-28-05 mtg,had minor requests. Mtg 3-29-05. 3-23-05 Cancelled mtg, FU mtg 3-28-05. 3-18-05 mtg, wanted lease to review, booked mtg 3-25-053-1605 booked mtg, 3-18-05. 3-12-05 reviewed & assigned; 3-2-05 title completed, edited 3-11-05. Leased to Atlas America, 5 yrs, 1/8th, expires 2-24-2007, if not HBP, or released.
46 | 57-23-00-0-060; 57-23-00-0-062 | Diebold | Frank E. & Patricia A., h/w | Box 157 | Crabtree | PA | 15624 | 724-838-0237 | 77.62 | 77.62 | [5 empty] | 03/15/07: called lessor but unavailable. Left message to get back to me as soon as possible. 03/13/07: mailed offer letter 02/26/07: left message 12/02/06: Prepared pkg and mailed w/ supporting GLEP information 11/29/06: not interested 11/27/06: msg w/ wife; he's away at camp until 11/29/06 11/22/06: Attempted contact, left message. 11/18/06: Attempted contact. 6-29-06 cb @ 2pm 6-3-06 lm 5-25-06 MOL 3-30-06 LM.3-29-05 Offered $4/ac bonus, $4/ac/yr rental, 1/8th roy. 5yr term, riders 1,2, 3.;"not wanting land disturbed." 3-16-05 Recovering from hosiptal stay, booked mtg 3-29-05. 3-12-05 reviewed & assigned; 2-28-05 title completed, edited 3-11-05. Leased to CNG Development 5 yrs, 1/8th, expired 4-3-1991, if not HBP.
47 | 61-03-00-0-011; 61-03-00-0-014; 61-03-00-0-017; 61-03-00-0-013; 61-03-00-0-016; 61-03-00-0-015; 61-03-00-0-025; 61-03-00-0-068; 61-03-00-0-069; 61-03-00-0-088 | Butz | Raymond M. & Dorothy A., h/w | 145 Butz Road | Latrobe | PA | 15650 | 724-539-8341 | 100 | 100 | 100 |  | 400 |  | GLEP | SIGNED 4-1-05 $4ac B $4ac/yr R, 1/8th, 5yr term.3-23-05 Cancelled mtg, booked FU 3-28-05. 3-17-05 mtg, interested,left lease for review, booked mtg 3-25-05. 3-16-05 booked mtg 3-17-05. 3-12-05 reviewed & assigned; 3-2-05 title completed, edited 3-11-05.
48 | 57-23-00-0-012 & 50-04-00-0-001 | Durco | John J. Jr. & Carole A. | 1724 Lincoln Street | Latrobe | PA | 15650 | 724-838-9191 | 52.004 | 52.004 | 52.004 |  | 312.024 |  |  | 02/28/07: SIGNED $6/ac non-drilling CBMGL w/ ROWA 02/23/07: left message requesting mtg 01/29/07: left a msg to schedule a mtg one evening this week 01/18/07: left message (their mother signed our lease 1/12/07) 12/11/06: Left message. 12/05/06: Prepared mail out letter offers; mailed with supporting information 11/29/06: left msg 11/27/06: Unavailable. 11/18/06: will schedule mtg for week after Thanksgiving 7-12-06 Carole called; answered ?'s; will call back to set up mtg. 6-29-06 LM 6-6-06 MOL. able to add to ex A stick to bound lines/rdways 5-12-05 Offered $4ac b, $4ac yr R, 1/8th roy., 5yr term, riders 1,2, 3. Atty advised not to sign because of perpetual ROW. 5-2-05 Atty will email request. 4-15-05 mtg, decided to let atty review.4-14-05 mtg, wants to sign on 4-15-05. 4-11-05 booked mtg 4-14-05.4-5-05 cld, wants to FU 4-11-05. 4-2-05 Wants to call him on 4-4-05. 3-28-05 mailed lease. 3-25-05 Interested, mailed CBM info. Leased to Doran & associates, Inc. 3 yrs, 1/8th, expired 4-9-1988, if not HBP.
49 | 61-03-00-0-019 | Horne | John P., (marital status unknown) | 838 Spring st. | Latrobe | PA | 15650 | 724-532-0649 | 31.5251 | 31.5251 | 31.525 |  | 126.1 |  | GLEP | SIGNED: 4-22-05 $4/ac bonus, $4/ac/yr rental, 1/8th, 5yr term. 4-13-05 mtg for 4-22-05.4-7-05 LM.4-2-05 cld, lessor interested, very busy(Doctor) said call me next week. 3-25-05 LM. 3-16-05, LM.3-12-05 reviewed & assigned; 3-3-05 title completed. Leased to MAC-MAR, Inc. 3 mos, 1/8th, expired 2-15-1992, if not HBP.
50 | 50-10-00-0-011 | Westmoreland County, a municipality | government tract | County Square | Greensburg | PA | 15601 |  | 180.7961 | 180.7961 | [5 empty] | DO NOT CONTACT. 3-25-05 reviewed & placed on hold, 3-14-05 title completed.
51 | 61-05-00-0-104 | Ruoff | Gregory B.( marital status?) | 213 Calvary Hill Rd. | Latrobe | PA | 15650 | 724-837-7799 | 32.75 | 32.75 | 32.75 |  | 131 |  | GLEP | SIGNED $4ac B, $4ac/yr R, 1/8th, 5yr term.agreed to sign, will leave signed lease for pick up on 6-13-05 6-2-05 Had to cancel mtg, had to work. Said he would call 6-8-05. .5-11-05 Nobody home.4-19-05 mtg, booked mtg 4-21-05. 4-15-05Will call me 4-16-05. 4-13-05 mtg, took lease to review.4-7-05 LM. 3-29-05 interested, busy, wants to call me this week.3-25-05 reviewed & posted; 3-13-05 title completed. O&G leased to Atlas America, Inc. 5 yrs, 1/8, expires 1-17-2008 if not released, or HBP, see 003/23145.
52 | 50-04-00-0-008 | Huffman | Elizabeth A., (marital status?) | 12675 Fairbrook Road | San Diego | CA | 92131 | 858-695-0689 | 79.14 | 79.14 | [5 empty] | 03/13/07: mailed offer letter 03/12/07: called lessor in San Diego, CA and left message on voicemail to call me as soon as she can regarding proposal 12/08/06: Mailed offer letter, GLEP information, and list of signed landowners 6-29-06 sent MOL to correct address 6-22-06 LM 5-17-06 LM. 4-5-06 mailed offer ltr & CBM info. 2-4-06 Offered $8B, $8R, 1/8th roy. 5yr term. Wants updated list of signed LO's,FU 3-4-06. 8-19-05 mailed updated list of signed LO's. 8-13-05 wants list of signed LO's. 7-5-05 LM. Wants call on 9-12-05. 7-2-05 No answer. 5-26 LM. 4-13-05 Offered $4/ac B, $4/ac/yr R, 1/8th roy., 5yr term, riders 1,4,6.; Wants FU call atend of May. 4-4-05 wants to discuss w/ husband.FU call on 4-11-05. 3-29-05 Mailed offer ltr.3-25-05 reviewed & posted; 3-17-05 title completed. No OGL of record.
53 | 50-10-00-0-051 | Harris | James E., Jr. & Nancy L., h/w | 51 Barnhart Rd. | Greensburg | PA | 15601 | 724-832-2560 | 88.6 | 88.6 | [5 empty] | 03/10/07: left message 02/26/07: left message 02/12/07: gave contact information and deadline of 2/20/07; left pkg for review 02/09/07: Prepared Non-Drilling CBMGL pkg 02/07/07: office # (724) 468-3548; Mtg 02/12/07 10:00 a.m. at his office 200 Brush Run Road 12/11/06: Received offer ltr & supporting information "It's under review but we are not taking any action right now". Willing to be updated if any changes are made. 12/02/06: Mailed offer letter and information 11/27/06: wife declared unintersted only permit info via mail; they'll "contact me at their convenience" 11/20/06: Attempted contact. 11/18/06: Attempted contact. 6-29-06 lm 6-22-06 LM. 4-5-06 Offered $12 B, $8 R, 1/8th roy., 5yr term, Atlas drilling co, is in the process of drilling 3rd well on tract; wants to wait, but conact him in couple months. 8-13-05 Offered $4/ac B, $4/ac/yr R, 1/8th roy., 5yr term, riders 1,4.6.; neighbors very upset, Atlas Drilling Co. drilled wells & one neighbor lost water source. 5-25-05 Stopped twice, nobody home. 5-16-05 Interested, but Atlas Drilling are drilling on tract, wants to discuss with wife.FU on 5-24-05. 5-12-05 LM. 5-2-05 Wants CBM info mailed for review. 3-25-05 reviewed & posted; 3-17-05 title completed. O&G leased to M.M.& V. Energy, LLC, 3 yrs, expires 10-11-2007 if not released, or HBP. See 004/71981.
54 | 50-11-00-0-096 | Battistella | Adam J. & Jayne M. (h/w) | RD 12 Matt Shields Ln. | Greensburg | PA | 15601 | 724-834-7580, 724-396-7527 (cell) | 151.67 | 151.67 | 151.67 |  | 910.02 |  | GLEP | 02/26/07: SIGNED $6/ac non-drill lease 01/22/07: prep/print pkg 01/20/07: MTG 1/25/07 11AM 12/11/06: Left message with wife. 12/04/06: cannot meet this week due to last weeks tornado 11/27/06: resched. mtg for weekend or beginning of next week. Unavailable due to nice weather 11/20/06: Attempted contact. 11/18/06: prep pkg, apt. set for 11/28/06 4-22-06 Offered $12 bonus, $8 rental, 18th roy, 5yr term, not at this time. 6-11-05 mtg,Offered $4/ac B, $4/ac/yr R, 1/8th roy. 5yr term, extensive riders, "not willing to sign a ROW agreement." 4-21-05 agreed to meet 5-4-05. 4-19-05 mtg, Left lease for review.4-13-05 Wants me to call back 4-20-05. 4-4-05 Wants me to mail CBM info. 3-29-05 Wants a few days to think about it. 3-25-05 reviewed & posted; 3-17-05 title completed. O&G leased to North Coast Energy, Inc., 5 yrs, 1/8, expired 7-3-2001, if not HBP. See 3543/67.
55 | 61-05-00-0-097 | Seanor, et al | Grace R. Seanor; Goldie I. Durco; William I. Ruffner, Jr.; Kathryn I. Neal (check all marital status) | c/o Mrs Kathryn Neal, 436 Three Degree Road | Renfrew | PA | 16053 |  | 45 | 45 | 45 |  | 270 |  |  | 02/05/07: Received copies of Ms. Seanor/Durco's husbands' obituaries and S. Bennett's POA 01/22/07: Bennett received POA; will sent it along with Ms.Seanor's husbands obituary this week 01/18/07: received Grace's social security number, completed processing pkg 01/17/07: Processed signed pkg, created highlighted maps, purchase reports, GLEP/GWM copies 01/16/07: mailed all interest holders copies of notarized CBMGL and ROWA 01/11/07: SIGNED FOR $6/ac Nondrilling lease with Blanket Right of Way Agreement 01/09/07: copy of Power Of Attorney will be coming from Buchannan's law office 01/08/07: left message for Susan Bennet verifying mtg location for 01/12/07 01/05/07: mtg 01/12/07 10:30am @ W. Ruffner's home with all 6 interest holders, reviewed and printed pkg & ROWA 01/04/07: mtg for 01/12/07 10:30am 01/03/07: spoke to Susan Bennett - she verbally committed to sign, phone mtg w/ Kathryn Neal: verified all interest holders spelling and addresses; prep standard & non-drilling CBMGL pkgs w/ ROWA 12/05/06: Prepared mail out letter offers; mailed with supporting information Held off on contact, reason, Goldie Durco's (Atty) see notes on tract #48. 4-21-05 reviewed & assigned; 3-30-05 title completed, received 4-13-05.
56 | 50-05-00-0-057 | Cerilli | Gregory B. & Lorraine M, h/w | 446 Cavalry Hill Road | Greensburg | PA | 15601 | 724-836-0948 | 75.48 | 75.48 | [5 empty] | 03/15/07: called lessor and left message, tried to locate residence because a mailout was returned but couldnt find house. 03/13/07: correct address is 446 Cavalry Hill Road, sent updated offer letter 01/22/07: mail was returned 12/18/06: address search; no other listing 12/11/06: Mail returned. 12/05/06: Prepared mail out letter offers; mailed with supporting information 11/22/06: Attempted contact, left message. 6-29-06 lm 6-22-06 sent MOL. 8-12-05 Offered $4/ac B, $4/ac/yr R, 1/8th roy., 5yr term, riders 1,4,6. response, no, reason, has plans of developing property. Lessor will not discuss any futher. 5-19-05 nobody home. 5-3-05 LM.5-2-05 LM. 4-21-05 reviewed & assigned; 3-31-05 title completed, received 4-13-05. Last O&GL North Coast Energy, Inc., 6 mos, 1/8, expired 12-7-96 if no HBP.
57 | 50-10-00-0-021 | G.E.S. Family Partnership, L.P. | c/o Erica Glasser | 55 East 9th St., Suite 9E | New York | New York | 10003 | 212-253-8003 | 112.27 | 112.27 | [5 empty] | 03/13/07: mailed offer letter 03/02/07: left message for Erica 12/05/06: Prepared mail out letter offers; mailed with supporting information 6-22-06 LM 4-5-06 mailed ltr offer $12 b, $8 r, 1/8th roy, 5yrtem. & CBM Info.8-13-05 LM,6-13-05 LM. 6-9-05 LM. .6-2-05 Wants me to call her back 6-6-05. 4-21-05 reviewed & assigned; 3-23-05 title completed & 4-13-05 delivered.
58 | 61-05-00-0-049 | Dunn | Charlotte E. & William M. (h/w) | 171 Rifle Lane | Latrobe | PA | 15650 | (724) 834-9460 | 87.076 | 87.076 | [5 empty] | 03/14/07: Sent mail out letter offers and updated information 12/02/06: Prepared pkg and mailed w/ supporting GLEP information 11/18/06: will not have mtg or consider leasing; "refuses to give up mineral rights" 6-29-06 LM 5-25-06 MOL 8-12-05 Offered $4/ac bonus, $4/ac/yr rental, 1/8th roy. 5yr term, riders 1,4,6.; very stern in his disinterest. "Not wanting land disturbed" not open for further discussion & not hurting for money. 5-11-05 no answer. 5-4-05 no answer 5-3-05 no answer,5-2-05 no answer. 4-21-05 reviewed & assigned; 3-30-05 title completed, received 4-13-05.
59 | 57-22-00-0-015 | Rugh | James D. & Janet E., h/w | 336 Stoney Springs Rd. | Greensburg | PA | 15601 | 724-837-2922 | 43.826 | 43.826 | [5 empty] | 03/16/07: stopped by residence but no answer, Left GLEP 03/14/07: Sent mail out letter offers and updated information 02/26/07: left message with wife; she took my info. but doesn't believe her husband will be intenrested 12/12/06: completed bring down, updated file, mailed offer ltr & supporting information, and prepared CBM Gas lease and ROWA pkg 11/27/06: unavailable until late evenings; took my info 11/22/06: Call Mon. to try to sched. an appt. (Dairy farmer; afternoons are best) 6-12-06 rude, not interested, slammed door in my face 6-3-06 NOT INTERESTED. 5-25-06 MOL 5-19-05 mtg: busy milking cows, wasn't friendly. 5-18-05 Nobody home. 5-3-05 Wife gave directions. 5-2-05 Offered $4/ac B, $4 ac/yr R, 1/8th roy., 5yr term, riders 1,2, 3. response,wife said to call back tomorrow.4-21-05 reviewed & assigned; 3-29-05 title completed, received 4-13-05.
60 | 61-05-00-0-048 | Platt | Carole, married (husband name unknown) | 1004 Elizabeth St. | Pittsburgh | PA | 15221 | 412-271-5685 | 103.47 | 103.47 | [5 empty] | 03/14/07: Sent mail out letter offers and updated information 01/18/07: Left message for Carole 12/11/06: Carole is the decision maker, she was unavailable 12/05/06: Prepared mail out letter offers; mailed with supporting information 6-16-06 No interest in leasing: intend on selling property. 6-3-06 best time week evenings 5-25-06 MOL 2-4-06 Not willing to sign at this time; might have buyer for tract, FU in April. 1-26-06 prep offer & payment ltr; mailed. 1-6-06 Offered $8 bonus, $8/ac/yr rental, 1/8th roy., 5yr term, w/Blanket row. Requested mail another lease pkg for review. 8-12-05 Gave same response to May offer.. not willing to negotiate. 5-12-05 Offered $4/ac B, $4/ac/yr R, 1/8th roy., 5yr term, riders 1,4,6; "not wanting to lease at this time, thinking about developing property." 5-11-05 LM. 5-3-05 Wants CBM mailed for review. 4-21-05 reviewed & assigned; 3-30-05 title completed, received 4-13-05.
61 | 61-05-00-0-016 | Shrum | Mary J. (confirm married to Paul J. Shrum) | 193 Calvary Hill Rd. | Latrobe | PA | 15650 | no phone listing | 46.8863 | 46.8863 | [5 empty] | 03/14/07: Sent mail out letter offers and updated information; stopped by lessors, spoke with wife, she said this is a bad time to try to catch her husband because it is tax season and hes an accountant. She said she would have him call me no later than friday. 03/02/07: mtg w/ Mrs. Shrum: Offered $6.00 per ac Non-Drilling CBMGL w/o ROWA - left contact information, husband will review and call for mtg 01/24/07: prp/print Non-drill pkg; spoke with daughter, best time to reach Lessor(s) is after/around 8:00 pm; took my information 12/02/06: Mailed offer letter and information 6-29-06 MOL 5-25-05 Offered $4/ac B, $4/ac/yr R, 1/8th roy., 5yr term, riders 1,4,6; "not interested, not wanting land disturbed." 5-18-05 wife said stop next week;discuss w/ husband. 5-2-05 no phone listing.4-21-05 reviewed & assigned; 3-30-05 title completed, received 4-13-05. OGL dated 9-9-1966, 1944/1013, several assignments, may be HBP.
62 | 61-05-00-0-014 | Leone | George H. & Helen E., h/w | 265 Leone Lane | Latrobe | PA | 15650 | 724-837-6016 | 54.006 | 54.006 | [5 empty] | 03/12/07: stopped by lessors and talked to husband, was nice but said there was no way to talk his wife into anything dealing with an oil and gas company. He wouldnt give me a chance to talk to her. 12/05/06: prep/mailed nonsurf pkg 11/27/06: wife won't permit a mtg; unsatisfied with ROW from Atlas 11/22/06: Call Mon. and try to set up a mtg 6-12-06 Offer $12B $8rent, wife is interference bc of Atlas Drilling Co misleading on compsensation for prop. damage. 2-26-06 Offered $12 B, $8ac R, 1/8th roy, 5yr term, said wife won't let him sign; Atlas broken promises. 8-13-05 Not willing to sign lease, still recovering from land disturbance from Atlas Drilling. Not willing to negotiate offer. 5-25-05 Offered $4/ac B, $4/ac/yr R, 1/8th roy., 5yr term, riders 1,2, 3.; Not wanting to do anything with CBM until Atlas Drilling cleans up their mess. 5-12-05 in Hospital. 5-3-05 Wants to discuss w/ wife. Booked FU call 5-9-05. 4-21-05 reviewed & assigned; 3-29-05 title completed, received 4-13-05. OGL dated 9-6-94, 10 years, multiple assignments, expired 9-6-04 if not HBP.
63 | 50-16-00-0-025, -27, -332, -333, -334 | Dillion | Walter Z. | 1027 Georgia Station Road | Greensburg | PA | 15601 | 724-834-5557 | 90.589 | 90.589 | 90.589 |  | 543.534 |  |  | 02/16/07: picked up copy of death certificate 02/02/07: $6/ac Non-drilling CBMGL w/o ROWA Processed signed pkg 02/01/07: mtg to sign 2/2/07 12:00 pm 01/29/07: no word yet from att. Ward: follow up Thursday @ his request. He will make a decision no matter what 01/23/07: no mtg w/ att. Ward & county set yet, follow up Friday 01/20/07: followed up from MTG with County & Attorney Ward; he has no questions or concerns, stated he wants to go through w/ execution 01/19/07: mtg from 8:30-11 with Westmoreland County representatives, attorney, and lessor 01/17/07: corrected lease pkg w/ new acreage, tax map #'s, money amounts, and new legal description 01/09/07: informed him of future mtg with GWM & Attorney Ward 01/08/07: plotted acquisition deed/outsales 01/03/07: mtg, question/answer session. Received attorney John Ward's information 12/20/06: unavailable 12/18/06: attorney was unavailable; stressed deadline for end of the week 12/16/06: attorney was out Fri. Follow up Mon 12/15/06: Waiting on attorney. 12/11/06: Att. has pkg call 12/13 12/07/06: resched. signing for the beginning of next week 12/04/06: son will review nonsurface pkg; follow up Wednesday 12/02/06: updated pkg 12/01/06: OFFERED $6/ac nonsurface lease w/o ROWA (1/2 surface sold: reserved coal) - verbally committed to sign. Follow up early in the week. 11/30/06: Mtg 12/1/06 10am 11/18/06: Attempted contact. 6-29-06 MOL per his request 6-3-06 unavailable 5-25-06 MOL 8-12-05 not willing to negotiate July offer. 7-2-05 Offered $4/ac B, $4/ac/yr R, 1/8th roy., 5yr term, riders 1,4,6; plan on selling off lots from tract. 6-18-05 Appeared to be home, nobody answered door; FU on 6-20-05. 6-8-05 mtg. not been able to meet with son to discuss lease; Son busy with work. FU on 6-14-05.
64 | 57-14-00-0-114 | Kepple | Robert S. Leonora H. | 202 Quarry Dr. | New Alexandia | PA | 15670 | 724-668-2834 | 154 | 154 | [5 empty] | 03/14/07: Sent mail out letter offers and updated information; correct address is 202 Quarry Drive 01/20/07: he wouldn't sign anything for less than $10/ac; still not interested - he said to call him back in a few months 11/24/06: Offered $6/ac Nonsurface CBM Gas Lease without ROWA: "Sounds like a good idea right now, but once activity starts happening it probably won't be." and "Taking it to the attorney will eat away too much of the rental money to make it worth it." They are just "not interested right now" and concerned about all the non-coal owners; their neighbor across the street is one. They also kept referring to Beldon & Blake's project in Indiana County 11/20/06: prep nonsurf CBMGL/ROW 11/18/06: mtg ste for 11/24/06 3-22-06 Discuss with his son's & their not wanting to sign at this time; "not sure if they want their land disturbed." FU in a couple months. 3-17-06 Offered $8 B, $8/ac/yr R, 1/8th roy., 5yr term. considering, wants to discuss with son, booked FU 3-22-06. 3-17-06 Title completed, assigned.
65 | 57-19-00-0-049 | Kepple | Charles W. & Donna L. & George L. Suzanne H. | 753 Hannastown Rd. | New Alexandia | PA | 15670 | 724-668-7776 | 39.689 | 39.689 | 39.689 |  | 476.27 |  | GLEP | 5-22-06 Resigned memorandum/lease bc of notary issues. SIGNED: 5-4-06 $12 B, $10 R, 1/8th roy, 5yr term + 5op, w/ Blanket rowa. 4-26-06 Discussed lease, wants same lease as William Smith. 4-19-06 MTG, offer $12B,$8R, 1/8roy; needs time. FU mtg schd 4-25-06.4-3-06 Wants to discuss with his brother, would call back next week for MTG. 3-31-06 Offered,$12 B, $8ac R, 1/8th roy, 5yr term, w/ blanket row. Booked FU call 4-3-06. 3-22-06 Wife said husband in bed, call back during the day 12pm. 3-14-06 Title completed & assigned.
66 | 57-19-00-0-027 | Selembo | William G. & Jeannie R. | 289 Rosewood Drive | Greensburg | PA | 15601 | 724-668-7955 (H) 412-558-0886 © | 117.224 | 117.224 | 117.224 |  | 1406.69 |  | GLEP | SIGNED: 3-31-06 $12 B, $8 R, 1/8th roy., 5yr term, w/ blanket row.3-21-06 mtg, Offered $8 bonus, $8ac rental,1/8th. roy., 5yr, term, considering, but wants me to check his other tract to see if he owns his coal. FU 3/28/06. 3-14-06 Title completed & assigned.
67 | 57-19-00-0-026 | Paluzzi | Gino F. & Linda F. Paluzzi | 1432 Poplar Street | Greensburg | PA | 15601 | 724-834-6121 | 62.482 | 62.482 | [5 empty] | 03/20/07: Offered $6/ac Non-Drilling CBMGL w/o ROWA: declined offer 03/14/07: Sent mail out letter offers and updated information 01/19/07: Lessor won't have a mtg to hear about nonsurf lease option - claims its all in his attorney's hands - stated they do not want to lease it at all and don't want any updates 11/20/06: Att. Whitehead is supposed to fax me any changes 7-21-06 atty Whitehead, he said he hasn't heard from atty Conti. Mr. Whitehead ask that I call back 7-25-06 to see if he has received proposed addendum to CBM lease. 6-12-06 waiting on atty 5-17-06 apt w/ Wayne Whitehead (atty) 5-17-06 11am. 5-8-06 discussed lease pkg/rowa, wants to review. FU 5-17-06. 4-17-06 interested, wants pkg mailed. 4-5-06 mailed ltr offer $12 B, $8 R, 1/8th roy, 5yr term, & CBM Info.3-25-06 Offered $8 B, $8 R, 1/8th roy, 5yr term. Wants CBM info mailed, not friendly. 3-18-06 Title completed & assigned.
68 | 57-19-00-0-123 | Propeties LLC | RMK | 619 Mansfield Road | Willow Grove | PA | 19090 | 215-657-8471 | 121.46 | 121.46 | [5 empty] | 02/05/07: owned by Robert J. Kepple; he attended mtg w/ his father, spoke w/ wife, they are still not interested 12/06/06: Mailed offer ltr w/ supporting information 6-29-06 MOL to right add. 4-5-06 mailed ltr offer $12 B, $8 R, 1/8th roy, 5yr term, & CBM Info. 3-18-06 Title completed & assigned.
69 | 57-19-00-048 | Beer | Richard G. | 596 Hannastown Road | Greensburg | PA | 15601 |  | 20.966 | 20.966 | [5 empty] | 03/16/07: Stopped by residence but unavailable, Left GLEP 02/05/07: sent follow up ltr asking for a mtg; no phone listing 01/15/07: he is married: wife answered but barely opened the door. Kept stating "we are not interested" 01/09/07: attempted contact; left GLEP notice on door 12/06/06: Mailed offer ltr w/ supporting information 3-31-06 mtg, didn't want to hear offer; bad experince with Gas Companies & not wanting land disturbed. 3-25-06 Title completed & assigned.
70 | 57-19-00-046 | Kemsey | Kevan B. & Sharon K. | 164 Tucker Road | New Alexandria | PA | 15670 | 724-668-7931 | 31.487 | 31.487 | [5 empty] | 01/19/07: mailed offer letter and supporting information Attended signing of Hiennickel Farms as notary 11/20/06: will agree to no mtg or receiving any information. "Anything you guys do I will fight it" 5-19-06 Kevan doesn't want to sign a lease, he may develop property. 4-20-06 GLEP notice. 3-31-06 Nobody home. 3-30-06 LM. 3-25-06 Title completed & assigned.
71 | 50-11-00-0-007 | Graham | Edward G. & Laura E. | RD9 Box 230 | Greensburg | PA | 15601 | 724-832-8991 | 10 | 10 | [5 empty] | 12/06/06: Mailed offer ltr w/ supporting information w/ non-surface pkg. 11/22/06: prep nonsurf. Pkg 11/20/06: very negative: barely approved of having pkg sent via mail- will not have a formal meeting 11/18/06: Attempted contact. 6-29-06 MOL 5-5-06 Title completed & assigned file no.: 323.
72 | 50-05-00-0-031 | Salandro (1) Defabo (2) | Russell (1) Jerome (2) | 278 Hannastown Road | Greensburg | PA | 15601 | 724-668-8436 | 27.408 | 27.408 | [5 empty] | 12/05/06: Prepared mail out letter offers; mailed with supporting information 5-18-06 wife took info, husband will contact me. 5-17-06 no answer. 5-5-06 Title completed & assigned file no.: 325.
73 | 57-14-00-0-120 | Kepple | Daniel H. & Deborah K. | 861 Hannastown Rd. | New Alexandria | PA | 15670 | (724) 668-8133 | 111 | 111 | [5 empty] | 03/15/07: mailed offer letter and updated list of signed landowners 01/20/07: unavailable; call back Mon. around 4:00 PM 12/11/06: "Ok to update in the future but just not interested right now" 12/04/06: Mailed offer letter & supporting information 6-5-06 Not willing to sign: wants more royalty (1/4); may devel. Tract. FU in few months. 5-16-06 Offered $12 b, $8 rent, 1/8th roy, 5yr term, w/blk rowa; Took GLEP info & blank lease pkg for review. FU 5-29-06. 5-5-06 Title completed and assigned file no.: 342.
74 | part of 50-05-00-0-037 | Lenz | Gary & Eleanor A. | 105 Macauley Rd. | Williamsburg | VA | 23185 |  | 60 | 60 | 60 |  | 1500 |  | GLEP | 11/18/06: Status review update - SIGNED for standard CBM Gas Lease and BROWA. 6-12-06 Mr. Lenz is waiting for pkg to come back w/ his att. FU Mon. 26 agreed to $1,000 sign bonus $500 yr rent. 6-3-06 FU next sat 5-22-06 answered questions, FU 5/29/06 after att. Reviews. 5-20-06 Offered $12/8, 5 yr term, wants drilled immediately, consult w/ GM FU 5/23/06. 5-16-06 MTG schd for 5-20-06. 5-10-06 Mailed offer ltr. 5-5-06 Title completed and assigned file no.: 343.
75 | 61-02-00-0-056 | Evans | Philip K. & Joan H., Philip K. Jr. | 329 Cemetery Rd. | Greensburg | PA | 15601 | (724) 834-6622 | 28.244 | 28.244 | [5 empty] | 02/26/07: no answer and no machine 01/20/07: unavailable, no answer and no machine 01/11/07: located 2 roads with the same name they could live on, no addresses matched 12/14/06: could not locate road 12/02/06: Mailed offer letter and information 11/30/06: unavailable 11/22/06: Attempted contact, unavailable.
76 | 61-02-00-0-071 | Evans | Philip K. & Joan H. | Box 317 | Crabtree | PA | 15624 |  | 64.725 | 64.725 | [5 empty] | 5-10-06 See comments above. 5-1-06 Title completed and assigned file no.: 339.
77 | 50-11-00-0-112 | Sekora | Michael | PO Box 200 | Luxor | PA | 15662 | (724) 834-3561 | 88.285 | 88.285 | [5 empty] | 12/02/06: Mailed offer letter and information 7-5-06 Lm 6-5-06 MOL 5-12-06 Business in Luxor, left signed LO's sheet, bus. Card, he'll be home in a few weeks. 5-6-06 Couldn't find home. 5-5-06 Title completed and assigned file no.: 341.
78 | 61-02-00-0-016 | Sekora | Michael | PO Box 200 | Luxor | PA | 15662 | (724) 834-3561 | 59 | 59 | [5 empty] | See Comments above. 5-5-06 Title completed and assigned file no.: 344.
79 | 61-05-00-0-105 | Kuhns | Rhet D. | 111 St. Cecilia Rd. | Latrobe | PA | 15650 |  | 69.187 | 69.187 | 69.187 |  | 830.24 |  |  | 5-19-06 SIGNED $12/8 W/ B. ROW scheduled 5-22-06.4pm 5-12-06 Cousin said FU tomorrow Lessor not available. 5-3-06 Title completed and assigned file no.: 338.
80 | 57-23-00-0-045 | Steel | Ralph & Rose (deceased) | 494 Hannastown Road | Greensburg | PA | 15601 |  | 97.5 | 70.543 | [5 empty] | 02/27/07: acreage needs changed to 97.5 surface acres; an entry below created for Jan Ondra; 26.957 acres leased 02/26/07: called lessor, but no answer, left message for them to get back in touch with me 01/11/07: left GLEP notice. 12/14/06: Offered $12/ac CBMGL/ROWA & $6/ac non-drilling CBMGL w/o ROWA: they do not want any kind of drilling; two brothers involved; Dwight works until evenings. Left my card - they will discuss and call me. 7-11-06 relative said they moved back into the house; sent MOL to correct address 6-29-09 Sent mail out letter offer to son Loren Steel, him and his brother will make the decisions regarding the property per Barbara (stepmother)
81 |  | Ondra | Jan | [5 empty] | 0 | 26.957 | 26.957 |  |  |  |  | See Comments above.
82 | 45-21-00-0-021; 45-21-00-0-023; 45-21-00-0-053; 45-21-00-0-048; part of 45-21-00-0-007; part of 45-21-00-0-009; part of 45-21-00-0-027 | Mumau | Helen J. | 204 N. Shenandoah Dr | Latrobe | PA | 15650 | (724) 532-0440 | 91.533 | 91.533 | [5 empty] | 03/14/07: Sent mail out letter offers and updated information 03/12/07: spoke with lessor, when I stated who I was and what I was calling for she hung up the phone. 03/05/07: stopped lessors but unavailable 01/20/07: "I don't want bothered"; she manages the property on her own, hung up on me 01/19/07: prep non-drill CBMGL pkg: found apartment complex, could not get in 01/09/07: attempted contact; left GLEP notice on door 7-11-06 Ms. Mumau is not interested, son has power of attorney over her but she doesn't want him contacted; not interested at all. 6-29-06 sent mail out ltr offer, glep info, cbm info, list of signed LO's. 6-7-06 Title complete and assigned file no.: 351.
83 | 61-05-00-0-026 | Leonard | Gary K. & Eleanor J. | 167 Luxor Road | Latrobe | PA | 15650 | (724) 537-5483 | 53 | 53 | [5 empty] | 12/02/06: Prepared pkg and mailed w/ supporting GLEP information 11/22/06: agreed only to receive via mail a list of signed landowners and supporting information after 10 minutes of pleading: will NOT have a meeting of any kind. "I'm REALLY not interested" is the only reason he gave numerous times. 7-11-06 husband is not interested at all. 7-5-06 wife took my info, will call me back to sched an appointment when husband avail. 6-28-06 Title complete and assigned file no.: 352.
84 | 61-03-00-0-040 | Earhart | Norman M. (marital status?) | 690 McChesney Road | New Alexandria | PA | 15670 | (724) 668-7338 | 129.193 | 129.193 | [5 empty] | 03/20/07: met with lessor at 1, Norman was on phone for 30 minutes while I spoke with wife. Finally came in for mtg but was very upset over a sickness in the family. He stated he wouldnt sign anything because he didnt want his surface disturbed. I explained to him this was a Non-surface lease but he informed me he wasnt in a good mental condition to be making a decision. Was told to give him a week and he'll meet with me again even though I told him that this was his last chance. Prep Non-Drilling CBMGL pkg for mtg 03/12/07: spoke with lessor, stated he would be out of town all week but will meet with me Tuesday 03-20-07 at 1:00 p.m. 02/26/07: not interested will not have a meeting 02/03/07: won't schedule a meeting at this time; his granddaughter is missing; he doesn't feel he can "think too good" 01/26/07: won't schedule a mtg due to family issues, call Mon/Tues 11/29/06: Lessor ill; follow up at end of week 11/27/06: Unavailable. 11/20/06: he'll contact current gas co. he is leased w/: doesn't believe there is no interference; call Tuesday 6-25-06 Title complete and assigned file no.: 348 to Tara Henry.
85 | 61-01-00-0-004 | Earhart | Norman M. | 690 McChesney Road | New Alexandria | PA | 15670 | (724) 668-7338 | 46.808 | 46.808 | [5 empty] | See #84 above. 6-27-06 Title complete and assigned file no.: 348.1 to Tara Henry. See above comments.
86 | 61-01-00-0-009 | Earhart | Norman M. Sr, Betty B. Earhart (h/w) | 690 McChesney Road | New Alexandria | PA | 15670 | (724) 668-7497 | 9.433 | 9.433 | [5 empty] | See #84 above. 6-27-06 Title complete and assigned file no.: 348.2 to Tara Henry.
87 | part 45-21-00-0-072-90-100 | A-One Land Trust |  | 44 Paul Revere Road | Oil City | PA | 16301 |  | 105.206 | 105.206 | [5 empty] | 7-15-06 Coal owned by Jan Ondra, confirm if leased to CBE and assigned to GLEP. Title complete and assigned file no.: 358.1.
87 | part 45-21-00-0-072 | Orgavan | John V. | 261 Flowers Road | New Alexandria | PA | 15670 | (724) 668-7087 | 211.421 | 211.421 | [5 empty] | 03/20/07: attempted to contact and set up meeting but unavailable, left msg to return my call. 03/19/07: attempted to contact lessor to confirm meeting but no answer. Was told to call before I showed up. Will follow up tomorrow. 03/12/07: spoke with lessor, set up meeting for monday 3-19-07 at 5:00. Was told to call lessor's cell phone on friday to confirm mondays mtg. 03/09/07: called lessor but unavailable so I drove out to lessors house but wasnt home. Left GLEP notice 02/26/07: add 724-668-7087; left message 02/05/07: wants to have a mtg, will call me with date he is available 01/24/07: prep CBMGL/ROW pkg, mailed offer ltr w/ supporting information, requested title for his other tract 45-21-00-0-027 7-5-06 Title complete and assigned file no.: 358 to Tara Henry.
88 | 61-05-00-0-076 | Ulicny | Edward A. & Mildred V. | 18399 Spring Beach Drive | South Bend | IN | 46637 | (574) 277-0526 | 22 | 22 | [5 empty] | 02/05/07: "absolutely not interested" "prefer not to explain why" 01/22/07: prep non-drill pkg, printed to mail via his request 01/20/07: "Not really interested", "Not enough money involved" - agreed to receive Non-Drilling pkg via mail; Offered $6/ac paid up Non-Drilling lease, verified all lessor information 01/17/07: Left message. 01/09/07: left message 12/04/06: Mailed offer letter & supporting information 7-18-06 lm on answering machine/sent mail out information. 7-18-06 Title complete and assigned file no.: 355 to Tara Henry.
89 | northern portion of 50-05-00-0-037, 61-02-10-0-010, 61-02-10-0-009, 61-02-10-0-025, 61-02-10-0-007 | Consol |  | 1800 Washington Road | Pittsburgh | PA | 15241 | [8 empty] | 5-28-06 Title complete and assigned file no.: 343.1. Consol owns all coal.
90 | 50-16-00-0-023 | Adam Eidemiller Inc. |  | 1003 E. Pittsburgh Street | Greensburg | PA | 15601 |  | 217.339 | 217.339 | [5 empty] | 01/23/07: mailed offer letter & supporting information 7-17-06 Title complete and assigned file no.: 373 to Tara Henry.
91 | 61-02-00-0-024 | Stynchula | Frederick & Mary | 3177 Crabtree Road | Latrobe | PA | 15650 |  | 27.417 | 27.417 | 27.417 |  | 329.004 |  |  | 12/12/06: mtg to correct signatures 12/11/06: SOGNED $12/ac standard CBM Gas Lease w/o ROWA (Specific ROW already acquired) 12/08/06: mtg 12/11/06 9:30am 12/04/06: Mailed offer letter & supporting information 7-18-08 Title complete and assigned file no.: 354 to Tara Henry.
92 | 45-21-00-0-026; 45-21-00-0-025 | Gera, et al | Mark, Et al (see file) |  |  | PA |  | 724-694-2525 | 185.407 | [6 empty] | 7-1-06 Title complete and assigned file no.: 350 to Tara Henry. (serviceable area should be 108.887ac)
92 | 45-21-00-0-026; 45-21-00-0-025 | Gera | Mark, Trustee | Box 305 | Bradenville | PA | 15620 | 724-694-2525 |  | 185.407 | [5 empty] | 02/05/07: sent mail out information and offer Left messages Olga's # 724-537-7627 12/15/06: Left message. 12/04/06: Mailed offer letter & supporting information 7-1-06 Title complete and assigned file no.: 350 to Tara Henry.
93 | 51-16-00-0-004, 002 | Weidlein | George McNary et al | PO Box 290 | Greensburg | PA | 15601 |  | 108.197 | 0 | [5 empty] | 6-27-06 Title complete and assigned file no.: 372 to Tara Henry. (Surface only)
93 | 51-16-00-0-004, 002 | Greensburg Coal Co. | [7 empty] | 77.965 | [5 empty] | 6-27-06 Title complete and assigned file no.: 372 to Tara Henry.
93 | 51-16-00-0-004, 002 | Greensburg Coal Co. | [7 empty] | 29.978 | [5 empty] | 6-27-06 Title complete and assigned file no.: 372 to Tara Henry.
94 | 51-10-00-0-097, 152 | Betler | Frederick & Connie | 501 Saxman Rd | Latrobe | PA | 15650 |  | 45.885 | 0 | [5 empty] | 7-21-06 Title complete and assigned file no.: 371 to Tara Henry. (surface only)
94 | 51-10-00-0-097, 152 | Southwest National Bank of PA Trustees for | Stockholder of Keystone Coal & Coke Co. | South Main St | Greensburg | PA | 15601 |  | 0 | 45.885 | [5 empty] | 7-21-06 Title complete and assigned file no.: 371 to Tara Henry.
95 | 50-10-00-0-069 | Mangini Family | Limited Partnership | PO Box C229 | Crabtree | PA | 15624 | (724) 834-6049 | 82.32 | 82.32 | 82.32 |  | 493.92 |  |  | 03/12/07: meeting with Vince and Mrs. Mangini; completed paperwork, processed signed package 03/10/07: SIGNED $6/ac non-Drilling CBM Gas Lease w/o ROWA, processed signed package 03/05/07: attorney Zuzik will not give his approval; Vince wants to speak with him again 03/02/07: left message for Vince .07: talked to Vince, pkg has been taken to attorney Zuzik 01/04/07: spoke to Vince; attorney has not reviewed lease; need a week or two MTG w/ GWM 12/27/06: MTG Offered $6/ac nonsurface CBMGL with ROWA; took pkg for attorney to review 12/20/06: set up mtg for 12/27/06 9:30 am 12/18/06: attempted contact. 12/07/06: mailed letter offer and supporting information 03/17/05: title completed.
96 | 45-21-00-0-057 | Masengale | Lois J. | 195 Twin Oaks Rd. | New Alexandria | PA | 15670 | (724) 668-8830 | 27.6 | 27.6 | [5 empty] | 03/05/07: Offered $6/ac Non-drilling CBMGL; they are just not interested; add phone number 724-668-8830; will not share their concerns 03/02/07: GLEP notice left 02/27/07: add (724) 668-8830 01/24/07: met Mr. Masengale; he will talk to his wife and call me to schedule the meeting 01/15/07: Prep CBMGL pkg/printed, introduced myself to Lois, she took my card; recently signed with Kriebel and wants to double check with them that there is no interference, will call me to schedule and appointment 12/07/06: mailed letter offer and supporting information. 05/25/06: Title competed.
97 | 50-11-00-0-007; 61-05-00-0-005 | O'Donnell Graham | Edward G. & Laura E. | RD 9 Box 230 | Greensburg | PA | 15601 |  | 65.525 | 0 | [5 empty] | 04/06/06: Title completed.
97 | 50-11-00-0-007; 61-05-00-0-005 | Bennett, Jr. | James A. | UNK. | UNK. | UNK. | UNK. |  | 0 | 65.525 | [5 empty] | 04/06/06: Title completed.
98 | 50-10-00-0-159 | Carbone | Natale J. & Elizabeth | PO Box 172 | Crabtree | PA | 15624 | 724-853-8385 | 100 | 100 | 100 |  | 600 |  |  | 02/28/07: processed signed pkg; created purchase report, highlighted maps, GLEP/GWM copies, mailed notarized copies to Lessor 02/26/07: SIGNED $6/ac Non-drilling CBM Gas Lease w/o ROWA 02/23/07: went to meeting at 10 a.m., lessors wife rescheduled meeting for Monday 02-26-07 at 10 a.m. 02/21/07: mtg to sign 2/23/07 10am 02/20/07: wants to execute pkg this week; will talk w/ Vince Mangini first and call me to schedule an apt. 01/31/07: he will be away until 2/18/07; attorney has no major concerns - expressed he wants to sign. Follow up 2/20/07 01/20/07: per wife call back 9:00 AM Monday; Mangini will talk to him in the meantime 01/08/07: pkg taken to attorney Bill Stillwagon 12/27/06: MTG Offered $6/ac nonsurface CBMGL with ROWA; took pkg for attorney to review 12/20/06: set up mtg for 12/27/06 9:30 am 12/18/06: Left msg w/ Wife; will not meet before Christmas 12/15/06: Tract added.
99 | 61-02-00-0-028 | Urchick | Mike & Barbara A. | 11 Barnhart Rd. | Greensburg | PA | 15601 |  | 39.413 | 39.413 | [5 empty] | 01/18/07: long phone conversation, he refuses to have a meeting or sign his name "in 15 different places" to a document (sent via his request) that he admits he does not understand. He is unclear on horizontal drilling as well, but willing to be updated in the future if any changes are made 01/04/07: prep standard and non-drilling CBMGL w/ ROWA and mailed at his request 12/20/06: Prep/mailed offer letters w/ suppporting information 12/14/06: Title completed.
100 | 50-04-00-0-017 | Repasky | George S. | 904 West Newton Rd. | Greensburg | PA | 15601 | (724) 834-7068 | 50.12 | 50.12 | [5 empty] | 01/18/07: couldn't find the home, phone # is 724-834-7068; he is deceased, there is a widow. She is elderly and being hounded by another gas company right now - doesn't want bothered, said follow up in a year or two. 01/17/07: Prep CBMGL/ROWA pkg; couldn't locate dwelling 12/20/06: Prep/mailed offer letters w/ suppporting information 12/18/06: Title completed.
101 | 61-05-00-0-106, 61-02-00-0-070, 61-02-00-0-025, 61-02-00-0-073 | Jamison | John M. & Suzanne R. (h/w) | 171 Jamison Ln | Latrobe | PA | 15650 | (724) 834-7424 | 210.69 | 210.69 | [5 empty] | 03/22/07: rec'd call: made it clear if he wants to participate in CBM it needs to be decided soon. 03/09/07: add this informaiton to the status report: 61-02-00-0-070 40 acres; 61-02-00-0-025 108.5 acres; 61-02-00-0-073 1 acre; OFFERED $6/ac Non-Drilling CBM Gas Lease w/o ROWA, took package for attorney to review 03/07/07: printed acquisition deeds, tax sheets, prepared highlighted maps, bounded by section, non-drilling CBMGL pkg, proofed and printed for mtg 3/9/07 03/06/07: printed all tax sheets to review w/ GWM 03/02/07: brief mtg, scheduled mtg 3/9/07 10:00 am 02/28/07: stopped by lessors but nobody was at residence, will follow up tomorrow 02/05/07: sent mail out information and offer Left messages 01/17/07: Left message. 01/05/07: sent mail out offer letter and supporting information 12/22/06: Title completed.
102 | 50-11-00-0-091 | Koontz | Donald L. & Marylee | RD 12 Box 364 | Greensburg | PA | 15601 | (724) 836-2952 | 27.092 | 27.092 | [5 empty] | 03/20/07: attempted to contact lessor, unavailable 03/16/07: attempted to contact lessor, unavailable, left message to return my call as soon as possible 03/14/07: attempted to locate lessors current address but will not answer phone. Left message for lessor to call back as soon as possible. 03/09/07: called lessor and talked to wife, husband will return my phone call tomorrow 03/05/07: stopped by lessors but uanvailable, left GLEP 02/08/07: left message for Don giving him a deadline of 2/20/07 02/05/07: sent mail out information and offer Left messages 01/23/07: Lessor called; question/answer session, expressed interest in signing. "will probably go through with it" will call me again to schedule signing (has until Feb. 8th) 01/17/07: Left message. 01/05/07: sent mail out offer letter and supporting information 12/26/06: Title completed.
103 | 50-10-00-0-099 & 50-11-00-0-118 | Schimizzi | Richard A. & Edna M. | 124 McWilliams Road | Greensburg | PA | 15601 | (H) (724) 837-3363, (cell) 724-454-0926 | 78.987 | 66.487 | 66.487 |  | 398.922 |  |  | 01/27/07: SIGNED $6/ac Non-Drilling CBM Gas Lease with Blanket Right of Way Agreement 01/23/07: mtg to sign 1/27/07 10am unless Att. says otherwise before then 01/17/07: Lessor's attorney was away for a few days this week, he'll call me in the beginning of the week; again stated he wants to sign 01/15/07: Offered $12/ac standard CBMGL and $6/ac Non-drilling CBMGL w/ ROWA; he verbally committed to sign, lease is going to his nephew to review, will call me within the next 3 days 01/09/07: MTG 01/15/07 10:00 am completed both CBM Gas Leases w/ ROWA/proofed/printed 01/05/07: sent mail out offer letter and supporting information 12/20/06: Title completed.
104 | 61-03-00-0-097 | Ondra | Jan | 44 Paul Revere Road | Oil City | PA |  |  | 0 | 8 | 8 |  |  |  |  | 02/03/07: leased to Jan Ondra; colored correctly on the status map; needs to be marked acquired on the status report 01/18/07: Title completed.
105 | 61-03-00-0-061 | Ondra | Jan | 44 Paul Revere Road | Oil City | PA |  |  | 0 | 4.74 | 4.74 |  |  |  |  | 02/03/07: needs colored light green on Salem status map and marked acquired on the status report 01/19/07: Title completed.
106 | 61-03-00-0-112 | Todd | David E. & Diana L. | 529 Todd Lane | New Alexandria | PA | 15670 |  | 1.46 | 1.46 | [5 empty] | 02/03/07: Mailed offer letter and supporting information 01/19/07: Title completed.
107 | 61-03-00-0-119 | Friscarella | Vincent Jr. & Carolyn S. | 376 McChesney Rd. | New Alexandria | PA | 15670 | 724-539-9191 | 43.43 | 41.43 | 41.43 |  | 248.58 |  |  | 03/01/07: processed signed CBMGL and ROWA; created purchase reports, hilighted maps, GLEP and GWM copies 02/28/07: SIGNED FOR $6/ac CBMGL and 43.43 surface acres- ROWA 02/26/07: called lessor, but no answer, left message for them to get back in touch with me 02/23/07: mtg 2/28/07 6:00 pm 02/14/07: completed legal description and CBMGL & ROWA 02/08/07: phone converstion: question/answer session, will sched mtg for an evening next week; prep both leases & ROWA 02/03/07: Mailed offer letter and supporting information 01/19/07: Title completed.
108 | 61-03-00-0-119 | Ondra | Jan | 44 Paul Revere Road | Oil City | PA |  |  | 0 | 2 | 2 |  |  |  |  | 02/03/07: Leased to Jan Ondra; map will be scanned and sent for corrections to Salem status map 01/19/07: Title completed.
109 | 61-03-00-0-52, 61-03-00-0-120, 61-02-00-0-040, 61-03-00-0-117 | Marko | Ronald J. & Donna J. | 398 McChesney Rd. | New Alexandria | PA | 15670 |  | 18.503 | 9 | [5 empty] | 03/12/07: rinted all deeds, plotted tracts, corrected CBMGL pkg, mailed offer letter. Add tracts: 61-02-00-0-040 .199ac & 61-03-00-0-117 8.3042ac 01/19/07: Title completed.
110 | 61-03-00-0-52 & 61-03-00-0-120 | Ondra | Jan | 44 Paul Revere Road | Oil City | PA |  |  | 0 | 1 | 1 |  |  |  |  | 03/12/07: leased to Ondra 01/19/07: Title completed.
111 | 57-23-00-0-106 | Bacher | Randy | 234 Route 30 West | Ligonier | PA | 15658 |  | 0 | 72.285 | [5 empty] | 12/21/06: Title completed.
112 | 61-05-00-0-062 | Tapper | Jack D. & Kay Y. | 279 McWilliams Rd. | Greensburg | PA | 15601 |  | 17.173 | 17.173 | [5 empty] | 03/15/07: mailed offer letter and supporting information 03/10/07: Prep Non-Drilling CBM Gas Lease pkg 12/21/06: Title completed.
113 | 57-23-00-0-074, et. Al. | Hoschar et al |  | 1547 Route 819 | Greensburg | PA | 15601 |  |  | 158 | [5 empty] | 02/14/07: mailed offer letter and supporting information to top three interest holders 12/28/06: Title Completed. Multiple heirs
114 | 57-22-00-0-009 | Ondra | Jan; Allan M. Povanda | 196 Peaceful Ln. | Greensburg | PA | 15601 |  | 0 | 35.632 | 35.632 |  |  |  |  | 03/12/07: leased to Ondra 01/15/07: Title completed.
115 | 57-23-00-0-061 | Ondra | Jan; Allan M. Povanda | Rd 4 Box 209 | Greensburg | PA | 15601 |  | 0 | 80 | 80 |  |  |  |  | 03/12/07: leased to Ondra 01/15/07: Title completed.
116 | 61-03-00-0-056 | Branthoover | Bruce M. & Diane | 129 Todd Ln. | New Alexandria | PA | 15670 | 724-537-2558 | 2 | 2 | 2 |  | 12 |  |  | 02/27/06: SIGNED $6/ac (paid-up) non-drilling CBMGL w/o ROWA 02/24/07: mtg 2/27/07 6:00 pm; received titles back from various tracts owned by Lessor 02/23/07: reviewed Non-Drilling CBMGL Pkg; attempted to set up mtg, Lessor will pick an evening for this week, added phone numbner to status report: 724-537-2558 02/07/07: phone convo: question/answer session- he will call me in beginning of next week to set up mtg to sign 02/03/07: Mailed offer letter and supporting information 01/22/07: Title completed.
117 | 61-03-00-0-110 | Hill | Charles B. & Heather N. | 109 Todd Ln. | New Alexandria | PA | 15670 |  | 123.032 | 0 | [5 empty] | 01/22/07: Title completed.
118 | 61-03-00-0-110 | Ruffner | Isaac Herirs et.al. | [5 empty] | 0 | 123.032 | [5 empty] | 01/22/07: Title completed.
119 | 61-03-00-0-063, -060 | Marko | Ronald J. & Donna J. | 398 McChesney Rd. | New Alexandria | PA | 15670 |  | 21.958 | 21.958 | [5 empty] | 03/12/07: printed all deeds, plotted tracts, corrected CBMGL pkg, mailed offer letter. 03/10/07: Prep Non-Drilling CBM Gas Lease pkg 01/19/07: Title completed.
120 | 61-01-00-0-002 | McChensney | Glen N. III & Suzanne | 591 McChensney Rd. | New Alexandria | PA | 15670 | 724-668-8838 | 73 | 73 | 73 |  | 438 |  |  | 03/20/07: processed signed pkg; highlighted maps, purchase report, GLEP/GWM copies 03/19/07: Completed Purchase Report 03/16/07: SIGNED $6.00 acre/rental 1/8 royalty 03/15/07: met with lessor and set up second meeting for Friday at 2:30 p.m. 02/03/07: Mailed offer letter and supporting information 01/19/07: Title completed.
121 | 61-03-00-0-116 | Ferret | Jeffery A. & Leanne M. | 104 Todd Ln. | New Alexandria | PA | 15670 |  | 123.032 | 0 | [5 empty] | 01/22/07: Title completed.
122 | 61-03-00-0-116 | Ruffner | Isaac Herirs et.al. | [5 empty] | 0 | 123.032 | [5 empty] | 01/22/07: Title completed.
123 | 61-03-00-0-062 | Bozich | Michael C. & Sharon L. | 412 McChesney Road | New Alexandria | PA | 15670 |  | 10 | 10 | [5 empty] | 03/02/07: stopped by lessors but werent available, left GLEP notice 02/28/07: left message for them to return call as soon as possible 02/03/07: Mailed offer letter and supporting information 01/19/07: Title completed.
124 | 61-03-00-0-039, 003, 116, 110, 117 | Mitchell | Gloria M. | 448 McChesney Rd. | New Alexandria | PA | 15670 |  | 123.032 | 0 | [5 empty] | 01/15/07: Title completed.
125 | 61-03-00-0-039, 003, 116, 110, 117 | Ruffner | Isaac Herirs et.al. | [5 empty] | 0 | 123.032 | [5 empty] | 01/15/07: Title completed.
126 | 61-03-00-0-118 | Carasia | James J. Carasia Jr. & Georgina L. Capasso | 1320 Latrobe Crabtree Rd. | Latrobe | PA | 15650 | 724-532-1183 | 10.712 | 10.712 | [5 empty] | 03/02/07: stopped by lessors but werent available, left GLEP notice 02/03/07: Mailed offer letter and supporting information 01/25/07: Title complete
127 | 50-17-00-0-003; 61-08-00-0-010; 61-08-00-0-142 | Mains | Dale T. & Susan J. | 109 Twin Lakes Rd. | Latrobe | PA | 15650 | 724-834-8261 | 17.575 | 17.575 | [5 empty] | 02/03/07: Mailed offer letter and supporting information 01/24/07: Title complete.
128 | 50-17-00-0-007; 50-17-00-0-008 | Cusano | William | RD 12 Box 284 | Greenburg | PA | 15601 | 724-838-9654 | 12.335 | 12.335 | 12.335 |  | 148.02 |  |  | 02/17/07: SIGNED: $12/ac Standard CBMGL & ROWA; processed signed package 02/16/07: corrected CBM Gas Lease: proof/print pkg for signing 2/17/07 12:00pm 02/13/07: offered $12/ac paid up standard CBMGL w/ ROWA- he took package to review; will make a decision by 02/20/07 02/12/07: mtg 12/13/07 7:00 pm 02/03/07: Mailed offer letter and supporting information 1/30/07: Title complete.
129 | 50-10-00-0-035 | First Comomnwealth Bank |  | 654 Philadelphia St., PO Box 400 | Indiana | PA | 15701 |  | 158.083 | 158.083 | [5 empty] | 1/12/07: Title competed.
130 | 57-23-00-0-074 | Hoschar | Linda L. & Philip S. | 1547 Route 819 | Greensburg | PA | 15601 |  | 88.875 | 88.875 | [5 empty] | 12/28/06: Title Completed. Multiple heirs
130 | 57-23-00-0-074 | Carasea | Tony & Eleanor | 202 George St. | New Alexandria | PA | 15670 |  | 32.9167 | 32.9167 | [5 empty] | 12/28/06: Title Completed. Multiple heirs
130 | 57-23-00-0-074 | Carasea | Gerals & Catherine | 1140 Beaver Run Rd. | Greensburg | PA | 15601 |  | 13.1667 | 13.1667 | [5 empty] | 12/28/06: Title Completed. Multiple heirs
130 | 57-23-00-0-074 | White | Carole A. | 426 Hickory Dr. | Greensburg | PA | 15601 |  | 3.2917 | 3.2917 | [5 empty] | 12/28/06: Title Completed. Multiple heirs
130 | 57-23-00-0-074 | Carasea | Angelo | 946 Nicklaus Dr. | Laurel | MD. | 20708 |  | 3.2917 | 3.2917 | [5 empty] | 12/28/06: Title Completed. Multiple heirs
130 | 57-23-00-0-074 | Gigliotti | Carmelita | 42 Meadow Dr. | Greensburg | PA | 15601 |  | 3.2917 | 3.2917 | [5 empty] | 12/28/06: Title Completed. Multiple heirs
130 | 57-23-00-0-074 | Hinerman | Janet | 1124 Beaver Run Rd. | Greensburg | PA | 15601 |  | 3.2917 | 3.2917 | [5 empty] | 12/28/06: Title Completed. Multiple heirs
130 | 57-23-00-0-074 | Dominick | Joseph J. | Rd 1 | New Alexandria | PA | 15670 |  | 3.2917 | 3.2917 | [5 empty] | 12/28/06: Title Completed. Multiple heirs
130 | 57-23-00-0-074 | Dominick | Beverly A. | 1561 Buffenmeyer Rd. | Greensburg | PA | 15601 |  | 3.2917 | 3.2917 | [5 empty] | 12/28/06: Title Completed. Multiple heirs
130 | 57-23-00-0-074 | Dominick | Joseph J. |  | Latrobe | PA | 15650 |  | 3.2917 | 3.2917 | [5 empty] | 12/28/06: Title Completed. Multiple heirs
131 | 57-19-00-0-019, 25, 40, 92, 93 | Mining, Co. | Rosebud | 301 Market Street | Kittanning | PA | 16201 |  | 120 | 120 | [5 empty] | 02/03/07: Mailed offer letter and supporting information
132 | 50-10-00-0-087, 50-11-00-0-041-90-100 | Smith | William R. | RD2 Box 859 | New Alexandria | PA | 15670 |  | 23.978 | 0 | [5 empty] | 10/24/05: Title complete
132 | 50-10-00-0-087, 50-11-00-0-041-90-100 | Bacher | Randy | RR 3 Box 450 | New Alexandria | PA | 15670 |  | 0 | 23.978 | [5 empty] | 10/24/05: Title complete
133 | 50-10-00-0-087 | Smith | William R. | RD2 Box 859 | New Alexandria | PA | 15670 |  | 65.325 | 0 | [5 empty] | 10/24/05: Title complete
133 | 50-10-00-0-132 | Polinsky | Robert S. & Kimberly A. | 97 Barnhart Rd. | Greensburg | PA | 15601 |  | 1.5 | 0 | [5 empty] | 10/24/05: Title complete
133 | 50-10-00-0-096 | Jones | Kenneth & Sheri | RD 12, Box 449 | Greensburg | PA | 15601 |  | 1.165 | 0 | [5 empty] | 10/24/05: Title complete
133 | 50-10-00-0-095 | Pomponi | Robert D. & Elizabeth A. | RD 12, Box 448 | Greensburg | PA | 15601 |  | 0.382 | 0 | [5 empty] | 10/24/05: Title complete
133 | 50-10-00-0-094 | Gillespie | James & Dolores M. | RR 16, Box 447-A | Greensburg | PA | 15601 |  | 0.402 | 0 | [5 empty] | 10/24/05: Title complete
133 | 50-10-00-0-093 | Allwine | Robert F. & Mildred B. | RD 12, Box 447 | Greensburg | PA | 15601 |  | 0.402 | 0 | [5 empty] | 10/24/05: Title complete
133 | 50-10-00-0-087 | First Commonwealth Trust Co. |  | 654 Philadelphia St., PO BOX 400 | Indiana | PA | 15701 |  | 0 | 65.325 | [5 empty] | 10/24/05: Title complete
134 | 61-05-00-0-132 | Lechman | [13 empty] | 02/26/07: left message with Beth- took my contact information, he'll call to schedule a meeting
135 | 50-05-00-0-043, 044, 045, 046 | Branthoover | James M. & Frances M. | PO Box 316 | Crabtree | PA | 15624 |  | 39.6 | 36.6 | [5 empty] | 02/07/07: Title completed.
136 | 50-05-00-0-003, et. Al. | Jamison | John M. Heirs and or assigns | [5 empty] | 90.55 | 90.55 | [5 empty] | 12/13/06: Titel completed.
137 | 61-05-00-0-132 | Lechman | Aaron P. & Beth, et. Al. | 156 Luxor Rd. | Latrobe | PA | 15650 |  | 34 | 34 | [5 empty] | 03/05/07: Prepared Non-Drilling lease packge 02/06/07: Title completed.
138 | 61-08-00-0-092 | Betler | Dean | Rd 2 Box 302 | Latrobe | PA | 15650 |  | 41.1 | 41.1 | [5 empty] | 02/06/07: Title completed. Leasehold on coal, Oil & gas mineral by Kriebel Resources Co. dated 8/5/03
139 | 57-24-00-0-010 | Branthoover | James H. & Frances M. | PO Box 316 | Crabtree | PA | 15624 |  | 5.75 | 5.75 | [5 empty] | 2/6/07: Title completed.
140 | 45-21-00-0-027 | Orgovan | John V. | 261 Flowers Rd. | New Alexandria | PA | 15670 |  | 17.1 | 17.1 | [5 empty] | 01/26/07: Title completed.
141 | 50-05-00-0-059, 060 | Salandro | Family Trust 138 | 138 Salandro Ln | Greensburg | PA | 15601 |  | 21.295 | 21.295 | [5 empty] | 03/05/07: Prepared Non-Drilling lease packge 02/14/07: Title completed.
142 | 57-24-00-0-013, 046 | Salandro | Family Trust 206 | 206 Bardine Rd. | Alexandria | PA | 15670 |  | 1.5 | 1.5 | [5 empty] | See notes above. 02/14/07: Title completed.
143 | 61-01-00-0-007 | Lesser | Stephen P. & Patricia M. | RD 1 Box 599 | New Alexandria | PA | 15670 |  | 3.6 | 3.6 | [5 empty] | 01/20/07: Title completed.
144 | 61-01-00-0-010 | Lesser | Stephen P. & Patricia M. | RD 1 Box 599 | New Alexandria | PA | 15670 |  | 25.654 | 25.654 | [5 empty] | 01/20/07: Title completed.
145 | 61-02-00-0-013 | Dominick | Frank & Rose | 244 Calvary Hill Rd. | Latrobe | PA | 15650 |  | 0.707 | 0.707 | [5 empty] | 02/17/07: Title completed.
146 | 61-02-00-0-055 | Dominick | Frank & Rose | 244 Calvary Hill Rd. | Latrobe | PA | 15650 |  | 22.956 | 22.956 | [5 empty] | 02/17/07: Title completed.
147 | 61-05-00-0-013 | Ruffner | Barbara J. | 136 Luxor Rd. PO Box 166 | Luxor | PA | 15662 |  | 13.362 | 13.362 | [5 empty] | 02/15/07: Title completed.
CBMG LEASE TOTALS | [8 empty] | 4718.3943 | 9102.3162 | 3258.864 | 0 | 19554.858 | 0
35.8%
Have Tax Maps
|  | 50-03 | 50-11 | 57-22 | 61-03
|  | 50-04 | 57-15 | 57-23
|  | 50-05 | 57-19 | 57-24
|  | 50-09 | 57-20 | 61-01
|  | 50-10 | 57-21 | 61-02
NOTE: The Gross and net footage columns are incorrect, they reflect mixed data, specific row's are indicating footage & the blanket row's are indicating acreage; to be corrected.
| RIGHT-OF-WAYS REQUIRED: | [7 empty] | Gross ftg | Net ftg. | Footage | Footage | Money | Money |  | COMMENTS
[9 empty] | ROW FT. | ROW FT. | Acquired | Commit'd | Spent | Commit'd
A | 61-01-00-0-001 | Berger | Paul & Roxanne | RR 1, Box 511 | New Alexandria | PA | 15670 | 724-668-2045 ofc & 724-668-8839 hm | 1100 | 1100 | 1100 | 0 | 1 | 0 | GLEP | SIGNED 11-6-03: $3/ft when built, path approved by C. Carlson, plat attached as Exh. "A". Required along southern boundary 3578/0537, 28.559 acres.Esti 700ft.
B | 61-03-00-0-039 | Mitchell | Gloria M. | RR 1, Box 597 | New Alexandria | PA | 15670 | 724-537-8995 | 1450 | 1450 | 1450 |  | 1 |  | GLEP | SIGNED 11-22-03: Right of Way Agreement, with Confidential Right of Way Addendum, 1,500 ft approx. plat attached as Exh."A", consulted with Carl Carlson on path, (connects Berger to Dominion tap); $3/ft by measure built and Meter Site Agreement (50'x50') for $1,500 to be paid within 30 days following construction.
C | 57-19-00-0-041 | Kepple | James L. & Michelle L. | RD 2, Box 842 | New Alexandria | PA | 15670 | 724-668-8954 |  |  |  |  | 1 |  | GLEP | SIGNED 11-12-03: $1.50/ft for lines to carry gas from outside properties when built, not site specific. Location restrictions.
D | 57-19-00-0-119 | Kepple | James L. & Michelle L. | RD 2, Box 842 | New Alexandria | PA | 15670 | 724-668-8954 |  |  |  |  | 1 |  | GLEP | SIGNED 11-12-03: $1.50/ft for lines to carry gas from outside properties when built, not site specific. Location restrictions.
E | 57-24-00-0-031 | Frye | Wayne C. & Hope L. | RD 9, Box 264 | Greensburg | PA | 15601 | 724-668-2833 |  |  |  |  | 1 |  | GLEP | SIGNED 11-06-03: $1.50/ft for lines to carry gas from outside properties when built, not site specific. Location restrictions.
F | 57-23-00-0-058 | Frenchek | William T. & Karin M., h/w | 1041 Orchard Avenue | Greensburg | PA | 15601 | 724- 837-9030 | 45 | 45 | 45 |  | 1 |  | GLEP | SIGNED an "anywhere" ROWA (see rider limitations) for "foreign gas" $2/ft if/when built. (see CBM Gas Lease above) same date as CBM Gas Lease.
G | 61-03-00-0-011; 61-03-00-0-068 | Butz | Raymond M. & Dorothy A., h/w | 145 Butz Road | Latrobe | PA | 15650 | 724-539-8341 | 94.537 | 94.537 | 94.537 |  | 1 |  | GLEP | SIGNED an "anywhere" ROWA (see rider limitations) for "foreign gas" $2/ft if/when built. (see CBM Gas Lease above) same date as CBM Gas Lease.
H | 61-03-00-0-019 | Horne | John P., (marital status unknown) | 838 Spring st. | Latrobe | PA | 15650 | 724-532-0649 | 31.5251 | 31.5251 | 31.5251 |  | 1 |  | GLEP | SIGNED an "anywhere" ROWA (see rider limitations) for "foreign gas" $2/ft if/when built. (see CBM Gas Lease above) same date as CBM Gas Lease.
I | 61-05-00-0-104 | Ruoff | Gregory B.( marital status?) | 213 Calvary Hill Rd. | Latrobe | PA | 15650 | 724-837-7799 | 32.75 | 32.75 | 32.75 |  | 1 |  | GLEP | SIGNED an "anywhere" ROWA (see rider limitations) for "foreign gas" $2/ft if/when built. (see CBM Gas Lease above) same date as CBM Gas Lease.
J | 57-23-00-0-048; 57-23-00-0-088 | Smith | William R. & Carol S., h/w | 128 Bliss Lane | New Alexandria | PA | 15670 | 724-668-7745 Son 724-668-0059 | 116.598 | 116.598 | 116.598 |  | 1 |  | GLEP | SIGNED an "anywhere" ROWA (see rider limitations) for "foreign gas" $2/ft if/when built. (see CBM Gas Lease above) same date as CBM Gas Lease.
K | 57-19-00-0-050; 57-19-00-0-051; 57-19-00-0-161 | Smith | William R. & Carol S., h/w | 128 Bliss Lane | New Alexandria | PA | 15670 | parents 724-668-7745 Son 724-668-0059 | 123.156 | 123.156 | 123.156 |  | 1 |  | GLEP | SIGNED an "anywhere" ROWA (see rider limitations) for "foreign gas" $2/ft if/when built. (see CBM Gas Lease above) same date as CBM Gas Lease.
I | 61-05-00-0-104 | Ruoff | Gregory B.( marital status?) | 213 Calvary Hill Rd. | Latrobe | PA | 15650 | 724-837-7799 | 32.75 | 32.75 | 32.75 |  | 1 |  | GLEP | SIGNED an "anywhere" ROWA (see rider limitations) for "foreign gas" $2/ft if/when built. (see CBM Gas Lease above) same date as CBM Gas Lease.
J | 57-19-00-0-027 | Selembo | William G. & Jeannie R. | 289 Rosewood Drive | Greensburg | PA | 15601 | 724-668-7955 (H) 412-558-0886 cell | 117.224 | 117.224 | 117.224 |  | 1 |  | GLEP | SIGNED an "anywhere" ROWA (see rider limitations) for "foreign gas" $2/ft if/when built. (see CBM Gas Lease above) same date as CBM Gas Lease.
K | 57-19-00-0-049 | Kepple | Charles W. & Donna L. & George L. Suzanne H. | 753 Hannastown Rd. | New Alexandia | PA | 15670 | 724-668-7776 | 39.689 | 39.689 | 39.689 |  | 1 |  | GLEP | SIGNED an "anywhere" ROWA (see rider limitations) for "foreign gas" $2/ft if/when built. (see CBM Gas Lease above) same date as CBM Gas Lease.
L | 61-05-00-0-105 | Kuhns | Rhet D. | 111 St. Cecilia Rd. | Latrobe | PA | 15650 |  | 69.187 | 69.187 | 69.187 |  | 1 |  | GM | SIGNED an "anywhere" ROWA (see rider limitations) for "foreign gas" $2/ft if/when built. (see CBM Gas Lease above) same date as CBM Gas Lease.
Total Pipelines | [8 empty] | 171.0621 | 171.0621 | 171.0621 |  | 12

## Sheet2
| CBM GAS LEASES |  | SIGNED BY CB ENERGY, OR NO LONGER DESIRED as of September 25, 2003
num'r |  | Last | First | Address | City | State | Zip | Phone |  |  | Acquired | Commit'd | Spent | Commit'd | LOC
Tr/map | Tax ID | Name | Name | grantor | grantor | grantor | Grantor | Contact | Gross Ac | Net Ac | Net Acre | Net Acre | Money | Money | of doc | Comments
| 50-04-008 | Huffman | Elizabeth A. | 12675 Fairbrook Rd. | San Diego | CA | 1560100% | 724-836-3068 | 63 | [6 empty] | 3179/242
| 50-05-057 | Cerilli | Gregory B. & Lorraine M. | RD 9, Box 217 | Greensburg | PA | 1560100% | 724-836-0948 | 75.5 | [6 empty] | 3137/92
| 50-10-011 | Westmoreland County | corporate | Courthouse Square | Greensburg | PA | 1560100% | 724- | 173 | [6 empty] | 2024/0024
| 50-10-021 | Lindwood Farms, Inc. |  | 460 Glemeade Rd. | Greensburg | PA | 1560100% | 724-836-1802 | 133.7 | [6 empty] | 3381/278 & 3373/412
| 50-10-051 | Harris | James E., Jr. & Nancy L. | 51 Barnhart Rd. | Greensburg | PA | 1560100% | 724-832-2560 | 88.6 | [6 empty] | 2829/283
| 50-10-069 | Manqini | Natalie C. | P.O. Box 229 | Crabtree | PA | 1562400% | 724- | 107.6 | [6 empty] | 3577/351
| 50-10-087 | Smith | William R. | RD 2, Box 859 | New Alexandria | PA | 1567000% | 724- | 76.1 | [6 empty] | 100/8165 & 3309/635
| 50-10-159 | Carbone | Natale J., III & Elizabeth | 730 Weldon St. | Latrobe | PA | 1565000% | 724-832-2560 | 100 | [6 empty] | 3577/346
| 50-11-096 | Battistella | Adam J. | RD 12, Matt Shields Lane | Greensburg | PA | 1560100% | 724-834-7580 & 724-836-3357 | 149.1 | [6 empty] | 3137/646
| 50-11-112 | Sekora | John P., III & Marilou E. | P.O. Box 200 | Luxor | PA | 1566200% | 724-834-3561 | 90 | [6 empty] | 2785/424
| 57-15-067 | Schlemmer | Robert W., Jr. | RD 2, Box 123 | New Alexandria | PA | 1567000% | 724-668-8242 | 26.8 | [6 empty] | 105/707
| 57-15-068 | Johnston Living Trust | Edward H. & A.kathleen | RR 2, Box 221 | New Alexandria | PA | 1567000% | 724-668-2193 | 158.2 | [6 empty] | 3739/407
| 57-15-078 | Pampena | Frank & Rose M. | 3712 Northern Pike | Monroeville | PA | 15146-2112 | 412-372-9159 | 35.9 | [6 empty] | 3255/90
| 57-15-112 | King | Patrick W. | RD 2, Box 781 | New Alexandria | PA | 1567000% | 724-668-2709 | 31.2 | [6 empty] | 2351/789
| 57-15-152 | Bragavich | Barbara A. | RD 2, Box 755 | New Alexandria | PA | 1567000% | 724- | 35.6 | [6 empty] | 3153/161
| 57-19-009 | Wright | John C. & Suzanne K. | RD 4, Box 317 | Greensburg | PA | 1560100% | 724-836-0620 | 88.9 | [6 empty] | 3004/637
| 57-19-027 | Hilty | John B. & Betty J. | RD 4, Box 135 | Greensburg | PA | 1560100% | 724-668-8309 | 126.4 | [6 empty] | 2025/581
| 57-19-092 | Selembo | William G. & Jeannie R | RD 4, Box 139B | Greensburg | PA | 1560100% | 724-668-7955 | 107.2 | [6 empty] | 2469/532 & 3443/625
| 57-19-123 | Bayle | Kenneth D. | RR 2, Box | New Alexandria | PA | 1567000% | 724-668-7086 | 121.2 | [6 empty] | 001/24156
| 57-19-26 | Paluzzi | Gino F. & Linda F. | 1432 Poplar St. | Greensburg | PA | 1560100% | 724-834-6121 | 61 | [6 empty] | 2960/324
| 57-20-012 | Marcheleta | Ralph F. & Karen | RD 2, Box 708 | New Alexandria | PA | 1567000% | 724-668-2354 | 39.5 | [6 empty] | 2071/1097
| 57-20-018 | Bowman | Donald B., Jr. & Jennifer L. (Life Est. to Violet) | RD 3, Box 253 | New Alexandria | PA | 1567000% | 724-668-2857 | 38 | [6 empty] | 2840/359 & 1099/195
| 57-20-082 | Bowman | Donald B. & Joyce Ann | RD 2, Box 690 | New Alexandria | PA | 1567000% | 724-668-2916 | 55.3 | [6 empty] | 2738/580 & 2008/95
| 57-22-009 | Sarver | Dwight K. & Anna K. | RD 3, Box 88 | Greensburg | PA | 1560100% | 724-834-3709 | 90.3 | [6 empty] | 2471/175, 2049/586 & 2047/326
| 57-23-045 | Steel | Ralph W. & Rose A. | RD 4, Box 133 | Greensburg | PA | 1560100% | 724-668-7718 | 104.7 | [6 empty] | 3222/271
| 57-23-058 | Frenchek | William T. & Karin M. | 1041 Orchard Ave. | Greensburg | PA | 1560100% | 724-837-9030 | 45 | [6 empty] | 3625/288
| 57-23-060 | Diebold | Frank E. & Patricia A. | Box 157 | Crabtree | PA | 1562400% | 724-838-0237 | 74.9 | [6 empty] | 3458/138
| 57-23-097 | Tanto | Tamas S. & Susan J. | RD 4, Box 121 | Greensburg | PA | 1560100% | 724-837-0572 & 724-837-4653 | 395.1 | [6 empty] | 3142/159
| 57-24-001 | Frye | Helen | Box 158 | Crabtree | PA | 1562400% | 724- | 67.4 | [6 empty] | 1069/330
| 57-24-024 | Slezak | Fred J. & Margaret S. | P.O. Box 407 | New Alexandria | PA | 1567000% | 724-668-8806 | 93.8 | [6 empty] | 3743/351
| 57-24-026 | Kiley | Mary Beth & John P., Jr. | 26420 Clancey St. | Roseville | MI | 4806600% | 586-776-7858 | 42.8 | [6 empty] | 0104/7844